## README
Data Analysis Automation Suite. Source repository: https://github.com/700imran/data-analysis-automation-script (reviewed at commit a04c40c). Requirements are reverse-engineered from the code and README.
Sheet | Purpose
Requirements Trace | Functional and non-functional requirements mapped to modules and verification evidence
Module Inventory | Files, size and role
Business Rules | Rules found in the code
Findings | Review findings with evidence and backlog link
Backlog | Proposed improvements (not built)
Claims Register | Benefit claims in the source docs and their evidence status
Verification | Checks executed and their results
RAID | Risks, assumptions, dependencies
Triage Matrix | Severity rules

## Requirements Trace
Req ID | Requirement | Priority | Module(s) | Verification / status
FR-01 | Load the latest data file automatically, or a named file from a default folder (.csv and .xlsx) | Must | latest_data_utils.py, default_folder.py | Verified by reading; path portability issue F-06
FR-02 | Standardise a raw dataset: lower-case snake_case column names, trimmed text, no duplicate or empty rows, numeric casting | Must | primary_clean_utils.py | Executed: 62 input rows, 60 output rows (2 duplicates removed), columns normalised, text trimmed
FR-03 | Run OLS regression for chosen predictors and a target and append fitted values (scenario analysis) | Must | analysis_utils.py, task_runner.py | Executed on seeded synthetic data: R-squared 0.436, n = 60 (0.789 with n = 58 when blanks are left out, see F-07)
FR-04 | Compute Pearson correlation and p-value between two numeric columns | Must | analysis_utils.py | Executed: r = 0.6179, p < 0.0001
FR-05 | Compare a metric between two groups with an independent t-test | Must | analysis_utils.py | Executed: t = -1.008, p = 0.318
FR-06 | Chart total of a metric by group | Should | analysis_utils.py | Not executed (needs display)
FR-07 | Compute valuation KPIs (P/E, P/B, earnings yield, dividend yield, valuation flag) for a market ticker | Should | kpi_utils.py | Not executed (needs live market data); call from task_runner mismatched, F-03
FR-08 | Derive forecast assumptions from live financial statements, including CAPM discount rate | Should | financial_metrics_utils.py | Not executed (needs live market data)
FR-09 | Project five years of revenue to free cash flow and derive enterprise value | Should | forecast_utils.py | Executed with default inputs: EV 30,393.81; see F-08
FR-10 | Build income statement, cash flow and balance sheet with shareholding pattern (three-statement model) | Could | cashflow_utils.py, balance_sheet_utils.py | Functions present; orchestration run_forecast missing, F-01
FR-11 | Save every result to a fixed 'live' file and optionally to a timestamped archive | Must | output_utils.py | Executed: fails when file path is None, F-05
FR-12 | Run any of six tasks from one entry point (run_task) | Must | task_runner.py | Import fails on a clean machine, F-01 and F-02
NFR-01 | Reusable functions callable from notebooks as well as from the runner | Should | - | Eight call notebooks in the repository
NFR-02 | Outputs consumable by Power BI / Excel (CSV and XLSX in a fixed folder) | Should | - | output_utils.py, kpi_utils.save_kpis
NFR-03 | Fail safely on missing statement labels from the market data provider | Should | - | safe_get() in financial_metrics_utils.py and forecast_utils.py
NFR-04 | Run on a fresh machine from the README alone | Must | - | Not met today: no requirements file, hard-coded paths (F-06, F-12)

## Module Inventory
File | Lines | Group | What it does | Depends on
task_runner.py | 137 | Orchestrator | run_task(task, filepath, ...) loads a file, applies basic cleaning, then runs one of six tasks: clean, scenario, relation, comparison, kpi, model | pandas, numpy, scipy, statsmodels, sklearn, openpyxl, yfinance (imports); all utility modules
latest_data_utils.py | 14 | Input | get_latest_data(folder): picks the newest .xlsx/.csv by creation time | os, glob, pandas
default_folder.py | 9 | Input | load_file(filepath): attaches the default input folder when only a file name is given | pandas (not imported, see F-04)
primary_clean_utils.py | 39 | Cleaning | clean_dataframe(df): normalises column names, trims strings, drops duplicates and empty rows, fills numeric NaN with 0, casts numeric-looking columns | pandas
analysis_target_entry.py | 21 | Analysis input | ask_for_columns(df): prompts for predictor columns and target | none
analysis_utils.py | 48 | Analysis | prepare_regression (OLS), check_correlation (Pearson), compare_groups (independent t-test), plot_sales_by_group (bar chart) | statsmodels, scipy, matplotlib
kpi_utils.py | 70 | Valuation KPIs | valuation_kpis(ticker): P/E, P/B, earnings yield, dividend yield and an over/undervalued flag; save_kpis writes CSV and XLSX | yfinance
financial_metrics_utils.py | 73 | Assumptions | get_assumptions(ticker): growth, COGS %, opex %, tax, capex %, depreciation %, working capital %, CAPM discount rate from live statements | yfinance
forecast_utils.py | 143 | Forecast | get_industry_metrics(industry), financial_forecast(...) five-year DCF projection, forecast_with_industry(...) | yfinance, pandas
cashflow_utils.py | 70 | Three-statement | compute_working_capital_change, compute_cash_flows (operating, investing, financing) | pandas
balance_sheet_utils.py | 125 | Three-statement | compute_working_capital_accounts, compute_balance_sheet, compute_shareholding_pattern | pandas
output_utils.py | 42 | Output | save_output(df, filepath, analysis_type): always overwrites a fixed 'live' CSV; optionally writes a timestamped archive | os, pandas, datetime
Total lines of Python | 791

## Business Rules
ID | Rule | Where
BRL-01 | Column names are lower-cased, trimmed and spaces become underscores | primary_clean_utils.py
BRL-02 | Leading and trailing spaces are removed from text values | primary_clean_utils.py
BRL-03 | Exact duplicate rows are dropped; fully empty rows are dropped | primary_clean_utils.py
BRL-04 | Missing numeric values are replaced with 0 | primary_clean_utils.py (see F-07)
BRL-05 | Columns that can be converted to numbers are converted | primary_clean_utils.py
BRL-06 | Regression rows with missing predictor or target are dropped before fitting; a constant is added | analysis_utils.py
BRL-07 | Correlation uses only rows where both columns are numeric | analysis_utils.py
BRL-08 | Group comparison is an independent two-sample t-test (equal variance assumed) | analysis_utils.py (see F-09)
BRL-09 | Discount rate (CAPM) = risk-free rate + beta x (market return - risk-free rate); defaults 7% and 12% | financial_metrics_utils.py
BRL-10 | Earnings yield above the government bond yield (default 7%) is flagged Undervalued, otherwise Overvalued | kpi_utils.py (see F-11)
BRL-11 | Industry benchmarks come from sector ETFs: Technology XLK, Retail XRT, Healthcare XLV, Financials XLF, Energy XLE | forecast_utils.py
BRL-12 | Forecast defaults: growth 10%, COGS 60%, opex 20%, tax 30%, capex 5%, depreciation 4%, working capital 10%, discount 12%, terminal growth 3%, 5 years | forecast_utils.py
BRL-13 | Terminal value = last-year FCF x (1 + g) / (discount - g), discounted to year 0; EV = sum of discounted FCF + discounted terminal value | forecast_utils.py
BRL-14 | Output file name = <input name>_<analysis type>_output.csv (live) and ..._<yyyymmdd_hhmm>.csv (archive, on request) | output_utils.py

## Findings
ID | Severity | Area | Finding | Evidence | Recommended fix | Backlog
F-01 | High | Reliability | run_forecast is imported by task_runner.py and documented in README, forecast.md and two notebooks, but is not defined in the committed forecast_utils.py. The cashflow and balance-sheet modules expect an income-statement table (Year, Revenue, COGS, Depreciation, EBIT, NetIncome) that no committed function builds. | Verified: hasattr(forecast_utils, 'run_forecast') is False; text search | Add run_forecast (or commit the local version) that builds the income statement and calls compute_cash_flows and compute_balance_sheet | DAA-101
F-02 | High | Reliability | latest_data_utils.py calls get_latest_data() at module level (the notebook example was left in the file), so importing it, and therefore task_runner, reads the input folder and raises FileNotFoundError when the folder is empty or missing. | Verified: import task_runner on a machine without the folder raises FileNotFoundError | Move the example under if __name__ == '__main__' | DAA-102
F-03 | High | Reliability | task_runner calls valuation_kpis(df, predictors, target, ticker) but the function is defined as valuation_kpis(ticker_symbol, gov_bond_yield=0.07). The kpi task would raise TypeError, and it prompts for predictors it never uses. | Verified: inspect.signature | Call valuation_kpis(ticker) and remove the unused prompts | DAA-103
F-04 | Medium | Reliability | default_folder.py uses pd.read_excel / pd.read_csv without importing pandas. | Verified: load_file raises NameError | Add import pandas as pd | DAA-104
F-05 | Medium | Reliability | save_output builds the file name from os.path.basename(filepath); when the runner auto-selects the latest file, filepath is None and every task fails at the save step. | Verified: save_output(df, None, 'clean') raises TypeError | Return the picked path from get_latest_data and pass it on | DAA-105
F-06 | Medium | Portability | Input and output folders are hard-coded to C:\Users\Dell\... in default_folder.py, latest_data_utils.py, output_utils.py and kpi_utils.py; output_utils creates its folder at import time. | Read from code | Single configuration (environment variable or YAML) with sensible defaults | DAA-106
F-07 | Medium | Data quality | clean_dataframe replaces every missing numeric value with 0. Zeros are then treated as real observations by the mean, regression and t-test, which biases results silently. | Verified on seeded synthetic data: two missing numbers became 0; regression R-squared fell from 0.789 (blanks left out, n = 58) to 0.436 (zero-filled, n = 60) | Configurable policy (leave missing, median, flag column) with a report of what was filled | DAA-108
F-08 | Medium | Model correctness | financial_forecast subtracts revenue x working-capital % each year as the working-capital change (a level, not a year-on-year change) and sets NPV to 10% of final-year FCF (a placeholder constant). With default inputs FCF is 2,200 on 1.1m revenue and EV is 30,393.81, so valuations are not reliable. | Verified by running defaults; formulas read from code | Use change in working capital; define NPV against an initial investment input; add a balance-sheet check | DAA-111
F-09 | Low | Statistics | compare_groups uses Student's t-test (equal variance). Welch's test is safer when group variances differ; no effect size is reported. | Read from code (scipy ttest_ind default) | Option for Welch; report mean difference and confidence interval | DAA-109
F-10 | Low | Output design | The relation task uses only the first predictor and writes the single correlation value into every row of the output. | Read from code | Output a one-row summary table or per-predictor table | DAA-110
F-11 | Low | Valuation logic | The valuation flag returns Overvalued whenever earnings yield is missing, and compares against a 7% bond yield default regardless of the ticker's market. | Read from code | Return 'Insufficient data'; make bond yield an input per market | DAA-103
F-12 | Low | Project hygiene | No requirements file, no tests, no setup steps in README, and the entry-point notebooks contain no recorded outputs for most tasks. | Verified by listing the repository | requirements.txt, pytest suite, setup section | DAA-107, DAA-113
F-13 | Info | Benefit claims | README and module notes state 70-80% faster workflows, 10-15 analyst hours saved a week, 20% faster and 10-12% more accurate valuations, 30-40% better reliability. The repository has no measurement behind these figures. | Verified by search for timings, baselines or logs | Measure on a sample workload and quote the measured figures (DAA-114); until then describe them as estimates | DAA-114

## Backlog
Rank | Key | Epic | Story | Persona | MoSCoW | Priority | SP | Status
1 | DAA-101 | DAA-E1 | Provide run_forecast and build the income statement | Analyst | Must | Highest | 13 | To Do
2 | DAA-102 | DAA-E1 | Remove import-time side effects | Analyst | Must | Highest | 2 | To Do
3 | DAA-103 | DAA-E1 | Fix the kpi task call and missing-data valuation flag | Analyst | Must | High | 3 | To Do
4 | DAA-104 | DAA-E1 | Add missing pandas import in default_folder | Analyst | Must | High | 2 | To Do
5 | DAA-105 | DAA-E1 | Support auto-selected files in save_output | Analyst | Must | High | 2 | To Do
6 | DAA-106 | DAA-E2 | Central configuration for input and output folders | Analyst | Must | High | 3 | To Do
7 | DAA-107 | DAA-E2 | requirements.txt and setup guide | New user | Must | Medium | 2 | To Do
8 | DAA-108 | DAA-E3 | Configurable missing-value policy with a fill report | Analyst | Should | Medium | 5 | To Do
9 | DAA-109 | DAA-E3 | Welch t-test option and effect size | Analyst | Should | Medium | 3 | To Do
10 | DAA-110 | DAA-E3 | Clear output for the relation task | Analyst | Should | Low | 3 | To Do
11 | DAA-111 | DAA-E4 | Correct working-capital change and NPV definition | Finance reviewer | Should | High | 5 | To Do
12 | DAA-112 | DAA-E4 | Three-statement integrity checks | Finance reviewer | Should | Medium | 8 | To Do
13 | DAA-113 | DAA-E5 | Automated tests for cleaning and analysis | Maintainer | Should | Medium | 5 | To Do
14 | DAA-114 | DAA-E5 | Benchmark harness for time and effort claims | Hiring manager or analyst | Should | Medium | 5 | To Do

## Claims Register
Where stated | Claim | Evidence status | Evidence found | Next step
README / task_runner.md | 70-80% faster analytics workflows | Not measured | No timings or baseline in the repository | Run DAA-114 and quote the result
README / task_runner.md | Saves 10-15 analyst hours per week | Not measured | No time study | Time a sample weekly workload before and after
task_runner.md | 30-40% improvement in reliability of analysis | Not measured | No definition of reliability | Define the metric (for example error rate on a known dataset)
forecast.md / README | 20% faster workflows and 10-12% more accurate valuations | Not measured; model inputs unvalidated (F-08) | No comparison against a reference valuation | Compare against a reference model after DAA-111
README | Reusable functions for cleaning, statistics, KPI and forecasting | Supported | Functions exist and the core ones were executed (cleaning, regression, correlation, t-test) | None

## Verification
ID | Item | Condition | Result | Detail
V-01 | clean_dataframe | Synthetic store dataset: 62 rows incl. 2 duplicates, padded text, mixed-case headers, 2 missing numbers | Pass | 60 rows returned, all columns snake_case, region values trimmed
V-02 | clean_dataframe | Missing numeric value in Store_Sales | Behaviour noted | Replaced by 0 and included in later statistics; mean sales 38,149 (blanks skipped) became 37,523 (F-07)
V-03 | prepare_regression | Sales on store area and daily customers, n = 60 after cleaning | Pass | R-squared 0.436; 0.789 when blanks are left out instead of zero-filled (F-07)
V-04 | check_correlation | Store area vs sales | Pass | r = 0.6179, p < 0.0001
V-05 | compare_groups | Sales by region North vs South | Pass | t = -1.008, p = 0.318 (no significant difference, as generated)
V-06 | financial_forecast | Default inputs | Runs | EV 30,393.81, NPV 322.10; FCF year 1 = 2,200 (F-08)
V-07 | import task_runner | Machine without the Windows input folder | Fail | FileNotFoundError at import (F-02)
V-08 | hasattr(forecast_utils, 'run_forecast') | Committed code | Fail | False (F-01)
V-09 | valuation_kpis signature | Committed code | Fail | (ticker_symbol, gov_bond_yield=0.07) vs call with four arguments (F-03)
V-10 | default_folder.load_file('x.csv') | Committed code | Fail | NameError: pd is not defined (F-04)
V-11 | save_output(df, None, 'clean') | Auto-selected file case | Fail | TypeError (F-05)
V-12 | kpi_utils, financial_metrics_utils, forecast_utils.get_industry_metrics | Live market data | Not executed | Needs internet access to the market data provider; to be run by the owner

## RAID
ID | Type | Description | Impact (1-5) | Probability (1-5) | Score | Owner | Response | Status
R-01 | Risk | Market data provider (yfinance) changes labels or limits access, breaking KPI, assumptions and benchmarks | 4 | 4 | 16 | Owner | safe_get() fallbacks exist; add contract tests with recorded responses | Open
R-02 | Risk | Valuation outputs are used for decisions while model formulas are unvalidated (F-08) | 5 | 3 | 15 | Owner | Label outputs as indicative until DAA-111/112 are done | Open
R-03 | Risk | Silent zero-fill biases analysis (F-07) | 4 | 4 | 16 | Owner | DAA-108 | Open
R-04 | Risk | Single maintainer; code runs only on one Windows machine | 3 | 4 | 12 | Owner | DAA-106, DAA-107 | Open
A-01 | Assumption | Input data arrives as CSV or XLSX with a header row | 4 | 2 | 8 | Owner | Validate headers on load | Open
D-01 | Dependency | Internet access to Yahoo Finance for KPI, assumptions and benchmarks | 4 | 3 | 12 | Owner | Cache last successful response | Open

## Triage Matrix
Severity | Definition | Action | Backlog position
High | Task cannot run from a clean checkout, or wrong numbers are produced silently | Fix first | Backlog rank 1-5
Medium | Works only on the owner's machine, or can bias results | Fix next | Backlog rank 6-12
Low | Output design or statistics refinements | Plan | Backlog rank 13+
Info | Documentation or evidence gaps | Plan | With DAA-114