## README
Mizan - simulated portfolio project. Fictional client, synthetic data. Blue header = table; edit data rows only.
Sheet | Purpose
Stakeholder Register | Who is involved, influence/interest, engagement strategy
RACI | Responsibility matrix per deliverable
Requirements Trace | BR/FR/NFR to epic/story/UAT traceability
Backlog | Prioritized sprint backlog with MoSCoW and story points
Sprint Velocity | Planned vs completed points (formulas)
RAID Log | Risks, assumptions, issues, dependencies with scoring formula
Change Log | Change control decisions
UAT | UAT cases and results
Defects | Defect log
Defect Triage Matrix | Severity and response rules
Exception Tracker | December 2024 exceptions from the reconciliation run (synthetic data); status and SLA breach are formulas
KPI Tracker | Match rate, clearance velocity and resolution KPIs computed by formula from the tracker

## Stakeholder Register
ID | Name (fictional) | Role | Project role | Influence | Interest | Strategy | Needs / notes
SH-01 | Maryam Al Hosani | Finance Controller | Sponsor and Product Owner | High | High | Manage closely | Owns scope, priority and go-live decision
SH-02 | Karthik Raman | Finance Manager | Approver, process SME | High | High | Manage closely | Wants approvals tracked and queryable; limits own approval queue to variances above AED 5,000
SH-03 | Sana Qureshi | Finance Analyst | Primary user | Medium | High | Keep informed, involve in UAT | Spends most of the day on VLOOKUP matching; wants fewer false breaks
SH-04 | Priya Menon | Revenue Accountant | User at month-end close | Medium | High | Keep informed | Cut-off errors from UTC vs GST dates; needs clean period totals
SH-05 | Omar Haddad | Head of Payments Partnerships | Gateway contracts, fee disputes | Medium | Medium | Keep satisfied | Needs fee evidence per transaction to dispute with gateways
SH-06 | Daniel Okafor | Engineering Lead | Delivery lead | High | High | Manage closely | Owns build estimates, ERP integration risk
SH-07 | Layla Siddiqui | QA Lead | Test owner | Medium | High | Keep informed | Needs testable rules and seed data
SH-08 | Nadia Farouk | Data Engineer (part-time) | Pipelines, data models | Low | High | Keep informed | Supports ingestion and views
SH-09 | Hassan Raza | Internal Audit | Audit evidence consumer | Medium | Medium | Keep satisfied | Needs immutable trail and period export
SH-10 | Rahul Nair | Scrum Master (part-time) | Ceremony facilitation | Low | Medium | Keep informed | Facilitates sprint cadence
SH-11 | Imran Kathat | Business Analyst | Requirements, process design, UAT coordination | High | High | Author | Single point for requirements traceability

## RACI
R=Responsible, A=Accountable, C=Consulted, I=Informed
Deliverable / activity | Controller (PO) | Finance Mgr | Analyst | Eng Lead | QA Lead | BA | Data Eng | Audit
Elicitation workshops and interviews | C | C | C | C | I | R/A | I | C
BRD authoring | A | C | C | C | I | R | I | C
BRD sign-off | A/R | C | I | C | I | R | I | I
Backlog prioritization (MoSCoW) | A | C | C | C | I | R | I | I
Gherkin acceptance criteria | A | C | C | C | C | R | I | I
Matching and tolerance rules definition | A | R | C | C | I | R | C | I
Fee schedule data supply | I | A | I | I | I | C | I | I
Build ingestion and matching | I | I | I | A/R | C | C | R | I
ERP integration | I | C | I | A/R | C | C | C | I
Test planning and fixtures | I | I | C | C | A/R | R | C | I
UAT execution | A | R | R | I | C | R | I | I
UAT sign-off | A/R | R | C | I | C | C | I | I
Change control decisions | A/R | C | I | C | I | R | I | I
KPI definitions | A | C | C | I | I | R | C | I
Audit evidence requirements | A | C | I | C | I | R | I | R
Go-live decision | A/R | C | C | C | C | R | I | I

## Requirements Trace
Req ID | Type | Requirement | Priority | Source stakeholder | Epic / Story | UAT cases
BR-01 | Business | Eliminate manual portal exports, spreadsheet matching and email approvals from daily reconciliation | Must | Finance Controller | MIZ-E1, MIZ-E4
BR-02 | Business | Reconcile every gateway settlement to a ledger invoice with net variance explained to AED 0.50 | Must | Finance Controller | MIZ-E2
BR-03 | Business | Every unmatched item has an owner, a flag and a due time | Must | Finance Manager | MIZ-E3
BR-04 | Business | Management can see match rate, clearance velocity and daily resolution rate without asking for spreadsheets | Should | Finance Controller | MIZ-E5
BR-05 | Business | Every adjustment is approved, posted and traceable for audit | Must | Internal Audit | MIZ-E4, MIZ-E5
FR-01 | Functional | Ingest gateway settlement batches via signed webhook with idempotency | Must | Finance Analyst | MIZ-101 | UAT-01, UAT-02
FR-02 | Functional | Detect and backfill missing batches by scheduled polling | Should | Finance Ops Lead | MIZ-102 | UAT-03
FR-03 | Functional | Match settlements to the latest non-void ledger invoice by gateway and transaction reference | Must | Finance Analyst | MIZ-103 | UAT-04
FR-04 | Functional | Price each settlement against the fee schedule effective on its settlement date, including 5% VAT on the fee | Must | Head of Payments | MIZ-104 | UAT-05
FR-05 | Functional | Report dates in GST and tag differences that are explained only by the UTC/GST boundary | Must | Revenue Accountant | MIZ-105 | UAT-06
FR-06 | Functional | Flag orphaned gateway and ledger records after a 3-working-day grace period | Must | Finance Analyst | MIZ-106 | UAT-07
FR-07 | Functional | Route exceptions to owner queues by flag | Should | Finance Ops Lead | MIZ-107 | UAT-08
FR-08 | Functional | Require manager approval above AED 5,000 with a 4-working-hour SLA and escalation | Must | Finance Manager | MIZ-108 | UAT-09, UAT-10, UAT-10R
FR-09 | Functional | Post approved journals to the ERP once, linked to the exception | Must | Finance Analyst | MIZ-109 | UAT-11, UAT-12
FR-10 | Functional | Provide KPI dashboard and exception tracker | Should | Finance Controller | MIZ-110 | UAT-13
FR-11 | Functional | Export period audit report with approver, timestamps and journal reference | Should | Internal Audit | MIZ-111 | UAT-14
NFR-01 | Non-functional | Process a 26,000-row monthly volume reconciliation in under 5 minutes | Must | Eng Lead | MIZ-103 | UAT-04
NFR-02 | Non-functional | Exception rows are append-only; no delete privilege for application roles | Must | Internal Audit | MIZ-108 | UAT-09, UAT-10, UAT-10R
NFR-03 | Non-functional | Store timestamps in UTC and display GST; weekend is Saturday-Sunday | Must | Finance Controller | MIZ-105 | UAT-06
NFR-04 | Non-functional | Webhook endpoint availability 99.5% in business hours with 15-minute fallback | Should | Eng Lead | MIZ-102 | UAT-03
NFR-05 | Non-functional | Keep financial records for 5 years (VAT) in a UAE-hosted region | Must | Internal Audit | MIZ-111 | UAT-14

## Backlog
Rank | Key | Epic | Story | Persona | MoSCoW | Priority | Story points | Sprint | Status
1 | MIZ-101 | MIZ-E1 | Webhook receiver with signature verification and idempotency | Finance Analyst | Must | High | 5 | MIZ Sprint 1 | Done
2 | MIZ-102 | MIZ-E1 | Scheduled polling fallback for missed batches | Finance Ops Lead | Should | Medium | 5 | MIZ Sprint 1 | Done
3 | MIZ-103 | MIZ-E2 | Match gateway settlements to ledger invoices within tolerance | Finance Analyst | Must | Highest | 8 | MIZ Sprint 2 | Done
4 | MIZ-104 | MIZ-E2 | Price settlements against fee schedule including VAT on fee | Head of Payments Partnerships | Must | Highest | 8 | MIZ Sprint 2 | Done
5 | MIZ-105 | MIZ-E2 | Classify UTC vs GST timing differences | Revenue Accountant | Must | High | 5 | MIZ Sprint 3 | Done
6 | MIZ-106 | MIZ-E3 | Detect orphaned records in both directions | Finance Analyst | Must | High | 5 | MIZ Sprint 3 | Done
7 | MIZ-107 | MIZ-E3 | Route exceptions to owners by decision table | Finance Ops Lead | Should | Medium | 5 | MIZ Sprint 3 | Done
8 | MIZ-108 | MIZ-E4 | In-tool approval with thresholds and SLA escalation | Finance Manager | Must | High | 8 | MIZ Sprint 4 | Done
9 | MIZ-109 | MIZ-E4 | Post journal adjustments to the ERP via API with idempotency | Finance Analyst | Must | High | 8 | MIZ Sprint 4 | Done
10 | MIZ-110 | MIZ-E5 | Reconciliation KPI dashboard and exception tracker | Finance Controller | Should | Medium | 5 | MIZ Sprint 5 | Done
11 | MIZ-111 | MIZ-E5 | Export reconciliation audit report for internal audit | Internal Auditor | Should | Medium | 8 | MIZ Sprint 5 | Done

## Sprint Velocity
Average velocity excludes Sprint 0 (discovery).
Sprint | Start | End | Committed SP | Completed SP | Completion % | Focus
Sprint 0 - Discovery | 2024-10-07 | 2024-10-18 | 0 | 0 | n/a | Elicitation, baseline, BRD v0.1
MIZ Sprint 1 | 2024-10-21 | 2024-11-01 | 10 | 10 | 100% | Webhook and polling ingestion
MIZ Sprint 2 | 2024-11-04 | 2024-11-15 | 16 | 16 | 100% | Matching and fee pricing
MIZ Sprint 3 | 2024-11-18 | 2024-11-29 | 15 | 15 | 100% | Timing, orphans, routing
MIZ Sprint 4 | 2024-12-02 | 2024-12-13 | 16 | 16 | 100% | Approvals and ERP posting (National Day 2-3 Dec)
MIZ Sprint 5 | 2024-12-16 | 2024-12-27 | 13 | 13 | 100% | Dashboard, audit export, hardening
Average velocity (Sprints 1-5) |  |  |  | 14
Total completed SP |  |  |  | 70

## RAID Log
ID | Type | Description | Impact (1-5) | Probability (1-5) | Score | Owner | Response / mitigation | Status | Raised
R-01 | Risk | Gateway webhook delivery is delayed or dropped during peak settlement windows | 4 | 3 | 12 | Daniel Okafor | Polling fallback every 15 minutes (MIZ-102); batch-gap alert | Mitigated | 2024-10-08
R-02 | Risk | Legacy ledger stamps posting dates in UTC for one entity, creating false month-end breaks | 4 | 4 | 12 | Imran Kathat | Timezone classification rule (MIZ-105); finance to confirm affected entity list | Mitigated | 2024-10-10
R-03 | Risk | ERP sandbox access delayed, blocking posting integration | 4 | 3 | 12 | Daniel Okafor | Mock ERP service with recorded contract; escalate via Controller by 25 Oct | Closed | 2024-10-09
R-04 | Risk | Analyst availability drops at month-end, slowing UAT feedback | 3 | 4 | 10 | Imran Kathat | Schedule UAT outside close window (30 Dec - 10 Jan, avoiding days 1-3 of month) | Closed | 2024-10-15
R-05 | Risk | Scope creep: refunds and chargebacks requested mid-project | 3 | 4 | 20 | Imran Kathat | Change control (CR-001); deferred to release 1.1 | Closed | 2024-11-12
R-06 | Risk | UAE National Day holiday (2-3 Dec) reduces Sprint 4 capacity | 2 | 5 | 15 | Rahul Nair | Sprint 4 commitment reduced; MIZ-110 moved to Sprint 5 | Closed | 2024-11-18
I-01 | Issue | ERP returns HTTP 429 when posting more than ~40 journals per minute | 4 | 5 | 10 | Daniel Okafor | Chunked posting with backoff and resume (MIZ-109 scenario 3) | Closed | 2024-12-04
I-02 | Issue | Re-issued invoices not voided in ERP produce two candidate matches per transaction | 3 | 5 | 15 | Imran Kathat | Latest non-void invoice rule via ROW_NUMBER (MIZ-103) | Closed | 2024-11-06
A-01 | Assumption | Gateways provide HMAC-signed webhooks and a batch-listing API | 5 | 2 | 12 | Omar Haddad | Confirmed in technical call with both gateways, 14 Oct | Validated | 2024-10-08
A-02 | Assumption | Contracted fee schedules are available per rail and effective date | 5 | 3 | 6 | Omar Haddad | Contracts supplied 21 Oct; one rail (AANI) missing, handled in CR-004 | Validated | 2024-10-08
D-01 | Dependency | ERP sandbox credentials and API documentation | 4 | 3 | 0 | Daniel Okafor | Delivered 29 Oct | Closed | 2024-10-09
D-02 | Dependency | Finance to supply 3 months of historical reconciliation spreadsheets for baseline | 3 | 2 | 0 | Sana Qureshi | Delivered 16 Oct | Closed | 2024-10-09

## Change Log
CR ID | Date | Requested by | Change | Impact assessment | Decision | Approvers | Status
CR-001 | 2024-11-12 | Maryam Al Hosani | Add refunds and chargebacks to the matching engine | +13 SP, 2 sprints; delays go-live by 3 weeks | Rejected for 1.0, added to release 1.1 backlog | Controller (decision), BA, Eng Lead | Closed
CR-002 | 2024-12-11 | Priya Menon | Count the orphan grace period in working days (SIT defect DEF-009: weekend false positives) | +1 SP; no date impact | Approved | Controller, QA Lead | Implemented 2024-12-18
CR-003 | 2024-11-20 | Karthik Raman | Reduce match tolerance from AED 1.00 to AED 0.50 | 0 SP; parameter change; re-baseline of test data | Approved | Controller, Finance Mgr | Implemented 2024-11-22
CR-004 | 2024-11-14 | Omar Haddad | Add AANI instant-payment rail to the fee schedule and test data | +2 SP | Approved | Controller, Eng Lead | Implemented 2024-11-29

## UAT
Case | Story | Scenario | Type | Tester | Result | Date
UAT-01 | MIZ-101 | Signed batch ingested and row count matches declared rows | Functional | Sana Qureshi | Pass | 2024-12-31
UAT-02 | MIZ-101 | Invalid signature rejected; no rows written | Security | Layla Siddiqui | Pass | 2024-12-31
UAT-03 | MIZ-102 | Missed batch is back-filled within 15 minutes | Functional | Sana Qureshi | Pass | 2025-01-02
UAT-04 | MIZ-103 | Exact, within-tolerance and beyond-tolerance rows classified correctly | Functional | Sana Qureshi | Pass | 2025-01-02
UAT-05 | MIZ-104 | Gateway overcharge detected with fee variance AED 27.56 on test row | Functional | Omar Haddad | Pass | 2025-01-02
UAT-06 | MIZ-105 | 30 Nov 21:40 UTC settlement tagged as timing mismatch | Functional | Priya Menon | Pass | 2025-01-03
UAT-07 | MIZ-106 | Weekend does not consume the orphan grace period | Regression | Priya Menon | Pass | 2025-01-03
UAT-08 | MIZ-107 | Each flag lands in the correct owner queue | Functional | Sana Qureshi | Pass | 2025-01-06
UAT-09 | MIZ-108 | Variance of AED 5,000.01 blocks posting until manager approval | Functional | Karthik Raman | Pass | 2025-01-06
UAT-10 | MIZ-108 | SLA escalation fires after 4 working hours | Functional | Karthik Raman | Fail | 2025-01-06
UAT-10R | MIZ-108 | Retest SLA escalation after fix DEF-013 | Retest | Karthik Raman | Pass | 2025-01-08
UAT-11 | MIZ-109 | Retry after timeout does not double-post | Functional | Layla Siddiqui | Pass | 2025-01-07
UAT-12 | MIZ-109 | Locked ERP period holds the adjustment with reason | Negative | Layla Siddiqui | Pass | 2025-01-07
UAT-13 | MIZ-110 | KPI cards match controller's manual December control totals | Functional | Maryam Al Hosani | Pass | 2025-01-08
UAT-14 | MIZ-111 | Audit export for closed December period complete | Functional | Hassan Raza | Pass | 2025-01-09

## Defects
ID | Title | Severity | Priority | Found in | Story | Status | Found | Fixed | Root cause
DEF-001 | Duplicate rows when webhook and poller race | S2 | P2 | SIT | MIZ-102 | Closed | 2024-11-05 | 2024-11-08 | Missing unique constraint on event key
DEF-002 | Tolerance applied to absolute gross instead of net | S1 | P1 | SIT | MIZ-103 | Closed | 2024-11-13 | 2024-11-14 | Wrong column in comparison
DEF-003 | Re-issued invoice produced two matches | S2 | P1 | SIT | MIZ-103 | Closed | 2024-11-06 | 2024-11-11 | Missing latest-invoice window rule
DEF-004 | VAT on fee rounded per row sum, not per row | S3 | P3 | SIT | MIZ-104 | Closed | 2024-11-15 | 2024-11-18 | Rounding applied after aggregation
DEF-005 | Fee schedule not effective-dated; mid-month rate change misprices | S2 | P2 | SIT | MIZ-104 | Closed | 2024-11-20 | 2024-11-25 | Join ignored effective_to
DEF-006 | Month-end settlement shown in wrong period in GST report | S2 | P1 | SIT | MIZ-105 | Closed | 2024-12-02 | 2024-12-05 | UTC date used for period bucket
DEF-007 | Dead-letter alert posted twice | S4 | P4 | SIT | MIZ-101 | Closed | 2024-11-07 | 2024-11-12 | Retry handler re-raised
DEF-008 | Owner empty for UNCLASSIFIED_VARIANCE | S3 | P2 | SIT | MIZ-107 | Closed | 2024-12-03 | 2024-12-04 | Missing default branch in routing table
DEF-009 | Paid Thursday invoice flagged orphan on Sunday | S2 | P1 | SIT | MIZ-106 | Closed | 2024-12-11 | 2024-12-18 | Grace counted calendar days (CR-002)
DEF-010 | Self-approval possible via direct link | S1 | P1 | SIT | MIZ-108 | Closed | 2024-12-12 | 2024-12-13 | Authorisation checked in UI only
DEF-011 | Posting retried after commit created second journal | S1 | P1 | SIT | MIZ-109 | Closed | 2024-12-16 | 2024-12-17 | Idempotency key not sent on retry
DEF-012 | KPI card shows 0% on Saturday | S4 | P4 | SIT | MIZ-110 | Closed | 2024-12-20 | 2024-12-23 | Non-working day not blank
DEF-013 | SLA escalation timer counts weekends | S2 | P2 | UAT | MIZ-108 | Closed | 2025-01-06 | 2025-01-07 | Timer used elapsed clock hours

## Defect Triage Matrix
Severity | Definition | Priority / action | Response SLA | Fix SLA
S1 Critical | Data loss, wrong money posted, security bypass | P1 - fix before next build; stop-ship | Same day | 4 hours
S2 Major | Core rule wrong, workaround exists | P1/P2 - fix in current sprint | 1 working day | 2 working days
S3 Moderate | Incorrect output in edge case, no money impact | P2/P3 - next sprint | 2 working days | Next sprint
S4 Minor | Cosmetic or logging | P4 - backlog | 3 working days | Backlog

## Exception Tracker
Synthetic December 2024 run. Clearance hours exclude Saturday/Sunday. SLA (working hours): timing 1; variance > AED 5,000: 4; fee dispute 120; orphan 48; other 24.
Exception | Txn ref | Flag | Variance AED | Owner | Opened (GST) | Resolved (GST) | Clearance (working h) | Status | SLA target (working h) | SLA check
EXC-8606 | TX2423001 | FEE_VARIANCE_BREACH | -2.03 | payments-partnerships | 2024-12-02 | 2024-12-06 10:16 | 96.26 | RESOLVED | 120 | OK
EXC-8258 | TX2410071 | FEE_VARIANCE_BREACH | -0.87 | payments-partnerships | 2024-12-02 | 2024-12-04 22:16 | 60.26 | RESOLVED | 120 | OK
EXC-8315 | TX2412182 | ORPHANED_LEDGER_RECORD | -137.11 | revenue-accounting | 2024-12-02 | 2024-12-05 06:17 | 68.29 | RESOLVED | 48 | BREACH
EXC-8316 | TX2412206 | FEE_VARIANCE_BREACH | -1.45 | payments-partnerships | 2024-12-02 | 2024-12-05 05:20 | 67.34 | RESOLVED | 120 | OK
EXC-8257 | TX2410049 | FEE_VARIANCE_BREACH | -4.3 | payments-partnerships | 2024-12-02 | 2024-12-05 23:47 | 85.78 | RESOLVED | 120 | OK
EXC-8431 | TX2417163 | ORPHANED_GATEWAY_RECORD | 62.04 | finance-ops-recon | 2024-12-02 | 2024-12-02 13:45 | 3.75 | RESOLVED | 48 | OK
EXC-8344 | TX2413620 | FEE_VARIANCE_BREACH | -0.9 | payments-partnerships | 2024-12-02 | 2024-12-06 09:54 | 95.91 | RESOLVED | 120 | OK
EXC-8376 | TX2414813 | UNCLASSIFIED_VARIANCE | -7.5 | recon-lead | 2024-12-02 | 2024-12-04 12:07 | 50.12 | RESOLVED | 24 | BREACH
EXC-8404 | TX2416257 | ORPHANED_GATEWAY_RECORD | 386.39 | finance-ops-recon | 2024-12-02 | 2024-12-03 08:13 | 22.22 | RESOLVED | 48 | OK
EXC-8568 | TX2421739 | FEE_VARIANCE_BREACH | -2.05 | payments-partnerships | 2024-12-03 | 2024-12-06 07:57 | 69.96 | RESOLVED | 120 | OK
EXC-8565 | TX2421649 | FEE_VARIANCE_BREACH | -0.9 | payments-partnerships | 2024-12-03 | 2024-12-09 19:09 | 105.15 | RESOLVED | 120 | OK
EXC-8545 | TX2420759 | FEE_VARIANCE_BREACH | -2.78 | payments-partnerships | 2024-12-03 | 2024-12-10 05:00 | 115 | RESOLVED | 120 | OK
EXC-8455 | TX2418105 | FEE_VARIANCE_BREACH | -1.96 | payments-partnerships | 2024-12-03 | 2024-12-06 18:16 | 80.27 | RESOLVED | 120 | OK
EXC-8427 | TX2417135 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8000 | TX2400001 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8324 | TX2412709 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8236 | TX2409370 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8242 | TX2409615 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8090 | TX2404033 | ORPHANED_GATEWAY_RECORD | 80.35 | finance-ops-recon | 2024-12-03 | 2024-12-04 22:14 | 36.23 | RESOLVED | 48 | OK
EXC-8111 | TX2404860 | ORPHANED_GATEWAY_RECORD | 200.61 | finance-ops-recon | 2024-12-03 | 2024-12-04 23:44 | 37.73 | RESOLVED | 48 | OK
EXC-8097 | TX2404504 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8027 | TX2401409 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8232 | TX2409148 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8252 | TX2409938 | ORPHANED_LEDGER_RECORD | -190.84 | revenue-accounting | 2024-12-03 | 2024-12-04 05:34 | 19.57 | RESOLVED | 48 | OK
EXC-8014 | TX2400765 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-03 | 2024-12-03 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8065 | TX2402917 | FEE_VARIANCE_BREACH | -1.08 | payments-partnerships | 2024-12-04 | 2024-12-11 10:31 | 120.52 | RESOLVED | 120 | BREACH
EXC-8414 | TX2416676 | FEE_VARIANCE_BREACH | -1.79 | payments-partnerships | 2024-12-04 | 2024-12-10 05:12 | 91.19 | RESOLVED | 120 | OK
EXC-8661 | TX2425315 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:23 | 0.38 | RESOLVED | 1 | OK
EXC-8331 | TX2412943 | FEE_VARIANCE_BREACH | -8.4 | payments-partnerships | 2024-12-04 | 2024-12-09 06:16 | 68.27 | RESOLVED | 120 | OK
EXC-8335 | TX2413169 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8501 | TX2419400 | FEE_VARIANCE_BREACH | -1.19 | payments-partnerships | 2024-12-04 | 2024-12-11 05:19 | 115.32 | RESOLVED | 120 | OK
EXC-8495 | TX2419224 | FEE_VARIANCE_BREACH | -3.5 | payments-partnerships | 2024-12-04 | 2024-12-10 22:28 | 108.47 | RESOLVED | 120 | OK
EXC-8222 | TX2408951 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8354 | TX2413943 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:30 | 0.5 | RESOLVED | 1 | OK
EXC-8054 | TX2402555 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8463 | TX2418467 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:04 | 0.06 | RESOLVED | 1 | OK
EXC-8182 | TX2407313 | FEE_VARIANCE_BREACH | -1.39 | payments-partnerships | 2024-12-04 | 2024-12-09 09:42 | 71.71 | RESOLVED | 120 | OK
EXC-8441 | TX2417566 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8392 | TX2415802 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8015 | TX2400814 | ORPHANED_GATEWAY_RECORD | 952.48 | finance-ops-recon | 2024-12-04 | 2024-12-04 21:20 | 11.33 | RESOLVED | 48 | OK
EXC-8543 | TX2420703 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8308 | TX2411948 | FEE_VARIANCE_BREACH | -0.59 | payments-partnerships | 2024-12-04 | 2024-12-11 03:58 | 113.96 | RESOLVED | 120 | OK
EXC-8610 | TX2423135 | ORPHANED_GATEWAY_RECORD | 32.38 | finance-ops-recon | 2024-12-04 | 2024-12-05 10:14 | 24.24 | RESOLVED | 48 | OK
EXC-8583 | TX2422276 | ORPHANED_LEDGER_RECORD | -789.23 | revenue-accounting | 2024-12-04 | 2024-12-06 17:39 | 55.64 | RESOLVED | 48 | BREACH
EXC-8556 | TX2421311 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8209 | TX2408309 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8292 | TX2411142 | FEE_VARIANCE_BREACH | -0.81 | payments-partnerships | 2024-12-04 | 2024-12-10 01:26 | 87.44 | RESOLVED | 120 | OK
EXC-8603 | TX2422896 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8279 | TX2410631 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8021 | TX2401306 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8102 | TX2404670 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8109 | TX2404820 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-04 | 2024-12-04 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8396 | TX2416007 | FEE_VARIANCE_BREACH | -4.22 | payments-partnerships | 2024-12-05 | 2024-12-09 10:14 | 48.23 | RESOLVED | 120 | OK
EXC-8676 | TX2425822 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8117 | TX2405086 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8298 | TX2411420 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8247 | TX2409681 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:23 | 0.39 | RESOLVED | 1 | OK
EXC-8305 | TX2411783 | UNCLASSIFIED_VARIANCE | -45 | recon-lead | 2024-12-05 | 2024-12-06 03:39 | 17.65 | RESOLVED | 24 | OK
EXC-8351 | TX2413816 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8653 | TX2425091 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8150 | TX2406183 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8285 | TX2410849 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8296 | TX2411246 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8267 | TX2410309 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:14 | 0.24 | RESOLVED | 1 | OK
EXC-8663 | TX2425398 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-05 | 2024-12-06 07:53 | 21.88 | RESOLVED | 24 | OK
EXC-8615 | TX2423228 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8230 | TX2409103 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-05 | 2024-12-09 08:02 | 46.03 | RESOLVED | 24 | BREACH
EXC-8599 | TX2422746 | FEE_VARIANCE_BREACH | -2.27 | payments-partnerships | 2024-12-05 | 2024-12-11 03:45 | 89.75 | RESOLVED | 120 | OK
EXC-8628 | TX2423792 | FEE_VARIANCE_BREACH | -3.8 | payments-partnerships | 2024-12-05 | 2024-12-09 21:26 | 59.43 | RESOLVED | 120 | OK
EXC-8596 | TX2422690 | FEE_VARIANCE_BREACH | -1.41 | payments-partnerships | 2024-12-05 | 2024-12-09 01:56 | 39.94 | RESOLVED | 120 | OK
EXC-8191 | TX2407773 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:09 | 0.14 | RESOLVED | 1 | OK
EXC-8634 | TX2424033 | FEE_VARIANCE_BREACH | -1.15 | payments-partnerships | 2024-12-05 | 2024-12-12 21:43 | 131.72 | RESOLVED | 120 | BREACH
EXC-8619 | TX2423309 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8035 | TX2401640 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8047 | TX2402202 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-05 | 2024-12-06 14:47 | 28.79 | RESOLVED | 24 | BREACH
EXC-8538 | TX2420384 | FEE_VARIANCE_BREACH | -1.6 | payments-partnerships | 2024-12-05 | 2024-12-11 09:51 | 95.85 | RESOLVED | 120 | OK
EXC-8522 | TX2419917 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8575 | TX2421852 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-05 | 2024-12-05 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8417 | TX2416746 | ORPHANED_GATEWAY_RECORD | 627.11 | finance-ops-recon | 2024-12-06 | 2024-12-09 18:04 | 32.07 | RESOLVED | 48 | OK
EXC-8281 | TX2410791 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8584 | TX2422353 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8211 | TX2408373 | FEE_VARIANCE_BREACH | -1.29 | payments-partnerships | 2024-12-06 | 2024-12-10 18:47 | 56.78 | RESOLVED | 120 | OK
EXC-8266 | TX2410272 | FEE_VARIANCE_BREACH | -1.58 | payments-partnerships | 2024-12-06 | 2024-12-12 13:04 | 99.07 | RESOLVED | 120 | OK
EXC-8592 | TX2422520 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8103 | TX2404674 | ORPHANED_GATEWAY_RECORD | 1074.17 | finance-ops-recon | 2024-12-06 | 2024-12-09 22:52 | 36.87 | RESOLVED | 48 | OK
EXC-8002 | TX2400061 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:18 | 0.29 | RESOLVED | 1 | OK
EXC-8303 | TX2411650 | ORPHANED_LEDGER_RECORD | -1104.3 | revenue-accounting | 2024-12-06 | 2024-12-11 06:40 | 68.66 | RESOLVED | 48 | BREACH
EXC-8112 | TX2404881 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8149 | TX2406172 | ORPHANED_LEDGER_RECORD | -297.1 | revenue-accounting | 2024-12-06 | 2024-12-11 12:56 | 74.93 | RESOLVED | 48 | BREACH
EXC-8309 | TX2411965 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8058 | TX2402722 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8122 | TX2405216 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8175 | TX2406997 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:13 | 0.21 | RESOLVED | 1 | OK
EXC-8482 | TX2419002 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-06 | 2024-12-06 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8546 | TX2420796 | FEE_VARIANCE_BREACH | -0.57 | payments-partnerships | 2024-12-06 | 2024-12-11 13:48 | 75.8 | RESOLVED | 120 | OK
EXC-8333 | TX2413006 | ORPHANED_GATEWAY_RECORD | 134.74 | finance-ops-recon | 2024-12-06 | 2024-12-09 02:56 | 16.93 | RESOLVED | 48 | OK
EXC-8190 | TX2407709 | FEE_VARIANCE_BREACH | -3.01 | payments-partnerships | 2024-12-09 | 2024-12-13 18:54 | 104.9 | RESOLVED | 120 | OK
EXC-8186 | TX2407471 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8225 | TX2408990 | FEE_VARIANCE_BREACH | -3.13 | payments-partnerships | 2024-12-09 | 2024-12-11 13:41 | 51.68 | RESOLVED | 120 | OK
EXC-8176 | TX2407122 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8208 | TX2408276 | FEE_VARIANCE_BREACH | -3.22 | payments-partnerships | 2024-12-09 | 2024-12-17 07:23 | 141.38 | RESOLVED | 120 | BREACH
EXC-8233 | TX2409155 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8173 | TX2406947 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-09 | 2024-12-10 21:37 | 35.61 | RESOLVED | 24 | BREACH
EXC-8156 | TX2406338 | ORPHANED_LEDGER_RECORD | -373.9 | revenue-accounting | 2024-12-09 | 2024-12-11 04:55 | 42.92 | RESOLVED | 48 | OK
EXC-8194 | TX2407819 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8199 | TX2407934 | ORPHANED_GATEWAY_RECORD | 778.97 | finance-ops-recon | 2024-12-09 | 2024-12-10 09:32 | 23.53 | RESOLVED | 48 | OK
EXC-8228 | TX2409071 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8372 | TX2414710 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8255 | TX2410026 | ORPHANED_GATEWAY_RECORD | 177.41 | finance-ops-recon | 2024-12-09 | 2024-12-11 13:35 | 51.58 | RESOLVED | 48 | BREACH
EXC-8674 | TX2425702 | ORPHANED_GATEWAY_RECORD | 123.89 | finance-ops-recon | 2024-12-09 | 2024-12-10 13:34 | 27.56 | RESOLVED | 48 | OK
EXC-8667 | TX2425542 | FEE_VARIANCE_BREACH | -0.6 | payments-partnerships | 2024-12-09 | 2024-12-12 19:30 | 81.5 | RESOLVED | 120 | OK
EXC-8666 | TX2425502 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:13 | 0.21 | RESOLVED | 1 | OK
EXC-8660 | TX2425268 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8655 | TX2425133 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8650 | TX2424848 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8648 | TX2424726 | FEE_VARIANCE_BREACH | -1.86 | payments-partnerships | 2024-12-09 | 2024-12-16 15:30 | 125.51 | RESOLVED | 120 | BREACH
EXC-8647 | TX2424643 | FEE_VARIANCE_BREACH | -0.78 | payments-partnerships | 2024-12-09 | 2024-12-13 20:01 | 106.02 | RESOLVED | 120 | OK
EXC-8639 | TX2424358 | ORPHANED_GATEWAY_RECORD | 95.17 | finance-ops-recon | 2024-12-09 | 2024-12-10 13:11 | 27.18 | RESOLVED | 48 | OK
EXC-8633 | TX2423954 | ORPHANED_GATEWAY_RECORD | 520.15 | finance-ops-recon | 2024-12-09 | 2024-12-10 13:50 | 27.83 | RESOLVED | 48 | OK
EXC-8587 | TX2422442 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:14 | 0.24 | RESOLVED | 1 | OK
EXC-8580 | TX2422205 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8563 | TX2421473 | ORPHANED_LEDGER_RECORD | -169.9 | revenue-accounting | 2024-12-09 | 2024-12-12 07:38 | 69.63 | RESOLVED | 48 | BREACH
EXC-8254 | TX2410020 | FEE_VARIANCE_BREACH | -2.63 | payments-partnerships | 2024-12-09 | 2024-12-10 23:20 | 37.33 | RESOLVED | 120 | OK
EXC-8550 | TX2421065 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8484 | TX2419028 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:03 | 0.06 | RESOLVED | 1 | OK
EXC-8470 | TX2418677 | ORPHANED_GATEWAY_RECORD | 182.1 | finance-ops-recon | 2024-12-09 | 2024-12-11 06:39 | 44.65 | RESOLVED | 48 | OK
EXC-8468 | TX2418634 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8440 | TX2417463 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8368 | TX2414541 | ORPHANED_GATEWAY_RECORD | 140.4 | finance-ops-recon | 2024-12-09 | 2024-12-11 01:32 | 39.53 | RESOLVED | 48 | OK
EXC-8359 | TX2414138 | FEE_VARIANCE_BREACH | -1.45 | payments-partnerships | 2024-12-09 | 2024-12-16 08:22 | 118.37 | RESOLVED | 120 | OK
EXC-8322 | TX2412619 | ORPHANED_LEDGER_RECORD | -147.37 | revenue-accounting | 2024-12-09 | 2024-12-12 14:15 | 76.26 | RESOLVED | 48 | BREACH
EXC-8320 | TX2412586 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8318 | TX2412425 | ORPHANED_GATEWAY_RECORD | 227.47 | finance-ops-recon | 2024-12-09 | 2024-12-11 06:18 | 44.3 | RESOLVED | 48 | OK
EXC-8307 | TX2411849 | FEE_VARIANCE_BREACH | -2.21 | payments-partnerships | 2024-12-09 | 2024-12-12 06:35 | 68.59 | RESOLVED | 120 | OK
EXC-8271 | TX2410424 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8268 | TX2410336 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8260 | TX2410098 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8542 | TX2420617 | FEE_VARIANCE_BREACH | -1.75 | payments-partnerships | 2024-12-09 | 2024-12-12 18:01 | 80.01 | RESOLVED | 120 | OK
EXC-8139 | TX2405802 | ORPHANED_LEDGER_RECORD | -487.82 | revenue-accounting | 2024-12-09 | 2024-12-12 11:27 | 73.46 | RESOLVED | 48 | BREACH
EXC-8339 | TX2413425 | FEE_VARIANCE_BREACH | -0.54 | payments-partnerships | 2024-12-09 | 2024-12-18 16:57 | 174.95 | RESOLVED | 120 | BREACH
EXC-8007 | TX2400306 | FEE_VARIANCE_BREACH | -0.74 | payments-partnerships | 2024-12-09 | 2024-12-17 13:21 | 147.36 | RESOLVED | 120 | BREACH
EXC-8008 | TX2400458 | ORPHANED_GATEWAY_RECORD | 258.52 | finance-ops-recon | 2024-12-09 | 2024-12-11 04:36 | 42.59 | RESOLVED | 48 | OK
EXC-8093 | TX2404176 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8055 | TX2402591 | FEE_VARIANCE_BREACH | -0.59 | payments-partnerships | 2024-12-09 | 2024-12-12 01:46 | 63.77 | RESOLVED | 120 | OK
EXC-8101 | TX2404645 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8062 | TX2402841 | ORPHANED_LEDGER_RECORD | -337.78 | revenue-accounting | 2024-12-09 | 2024-12-11 03:07 | 41.11 | RESOLVED | 48 | OK
EXC-8031 | TX2401501 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-09 | 2024-12-11 11:35 | 49.59 | RESOLVED | 24 | BREACH
EXC-8019 | TX2401189 | ORPHANED_LEDGER_RECORD | -339.23 | revenue-accounting | 2024-12-09 | 2024-12-11 16:07 | 54.11 | RESOLVED | 48 | BREACH
EXC-8085 | TX2403875 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8119 | TX2405113 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-09 | 2024-12-09 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8419 | TX2416857 | ORPHANED_LEDGER_RECORD | -34.58 | revenue-accounting | 2024-12-10 | 2024-12-10 23:10 | 13.17 | RESOLVED | 48 | OK
EXC-8608 | TX2423030 | FEE_VARIANCE_BREACH | -1.56 | payments-partnerships | 2024-12-10 | 2024-12-17 21:32 | 131.54 | RESOLVED | 120 | BREACH
EXC-8601 | TX2422778 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8643 | TX2424471 | FEE_VARIANCE_BREACH | -0.94 | payments-partnerships | 2024-12-10 | 2024-12-17 22:21 | 132.35 | RESOLVED | 120 | BREACH
EXC-8602 | TX2422780 | ORPHANED_GATEWAY_RECORD | 363.75 | finance-ops-recon | 2024-12-10 | 2024-12-11 18:09 | 32.15 | RESOLVED | 48 | OK
EXC-8439 | TX2417391 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8287 | TX2410944 | ORPHANED_LEDGER_RECORD | -92.37 | revenue-accounting | 2024-12-10 | 2024-12-13 11:20 | 73.33 | RESOLVED | 48 | BREACH
EXC-8071 | TX2403293 | UNCLASSIFIED_VARIANCE | -7.5 | recon-lead | 2024-12-10 | 2024-12-11 08:37 | 22.62 | RESOLVED | 24 | OK
EXC-8330 | TX2412899 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8552 | TX2421138 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:19 | 0.31 | RESOLVED | 1 | OK
EXC-8411 | TX2416591 | ORPHANED_GATEWAY_RECORD | 227.81 | finance-ops-recon | 2024-12-10 | 2024-12-12 21:37 | 59.62 | RESOLVED | 48 | BREACH
EXC-8221 | TX2408867 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8511 | TX2419709 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8403 | TX2416217 | ORPHANED_GATEWAY_RECORD | 93.67 | finance-ops-recon | 2024-12-10 | 2024-12-11 13:21 | 27.35 | RESOLVED | 48 | OK
EXC-8548 | TX2420908 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8123 | TX2405237 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8540 | TX2420603 | ORPHANED_LEDGER_RECORD | -419.92 | revenue-accounting | 2024-12-10 | 2024-12-16 17:35 | 103.59 | RESOLVED | 48 | BREACH
EXC-8076 | TX2403475 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8405 | TX2416268 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:15 | 0.24 | RESOLVED | 1 | OK
EXC-8167 | TX2406850 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8590 | TX2422485 | FEE_VARIANCE_BREACH | -2.29 | payments-partnerships | 2024-12-10 | 2024-12-13 00:42 | 62.71 | RESOLVED | 120 | OK
EXC-8672 | TX2425684 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8144 | TX2405994 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:06 | 0.11 | RESOLVED | 1 | OK
EXC-8454 | TX2418022 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8108 | TX2404818 | ORPHANED_LEDGER_RECORD | -246.43 | revenue-accounting | 2024-12-10 | 2024-12-13 20:20 | 82.33 | RESOLVED | 48 | BREACH
EXC-8445 | TX2417678 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-10 | 2024-12-10 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8570 | TX2421750 | FEE_VARIANCE_BREACH | -0.77 | payments-partnerships | 2024-12-10 | 2024-12-13 14:22 | 76.37 | RESOLVED | 120 | OK
EXC-8210 | TX2408332 | FEE_VARIANCE_BREACH | -1.26 | payments-partnerships | 2024-12-11 | 2024-12-16 20:33 | 82.55 | RESOLVED | 120 | OK
EXC-8582 | TX2422272 | ORPHANED_LEDGER_RECORD | -195.44 | revenue-accounting | 2024-12-11 | 2024-12-13 11:34 | 49.56 | RESOLVED | 48 | BREACH
EXC-8202 | TX2408054 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8038 | TX2401713 | ORPHANED_GATEWAY_RECORD | 52.38 | finance-ops-recon | 2024-12-11 | 2024-12-13 00:39 | 38.65 | RESOLVED | 48 | OK
EXC-8086 | TX2403876 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:20 | 0.34 | RESOLVED | 1 | OK
EXC-8352 | TX2413883 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8072 | TX2403308 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8573 | TX2421830 | ORPHANED_GATEWAY_RECORD | 200.97 | finance-ops-recon | 2024-12-11 | 2024-12-12 23:44 | 37.74 | RESOLVED | 48 | OK
EXC-8197 | TX2407906 | FEE_VARIANCE_BREACH | -1.53 | payments-partnerships | 2024-12-11 | 2024-12-18 07:33 | 117.56 | RESOLVED | 120 | OK
EXC-8397 | TX2416061 | ORPHANED_GATEWAY_RECORD | 67.3 | finance-ops-recon | 2024-12-11 | 2024-12-13 00:26 | 38.43 | RESOLVED | 48 | OK
EXC-8530 | TX2420127 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:24 | 0.41 | RESOLVED | 1 | OK
EXC-8458 | TX2418271 | ORPHANED_LEDGER_RECORD | -1134.42 | revenue-accounting | 2024-12-11 | 2024-12-13 18:43 | 56.72 | RESOLVED | 48 | BREACH
EXC-8357 | TX2413963 | UNCLASSIFIED_VARIANCE | -45 | recon-lead | 2024-12-11 | 2024-12-12 05:46 | 19.76 | RESOLVED | 24 | OK
EXC-8539 | TX2420398 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8325 | TX2412729 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8516 | TX2419784 | FEE_VARIANCE_BREACH | -0.91 | payments-partnerships | 2024-12-11 | 2024-12-11 11:41 | 1.69 | RESOLVED | 120 | OK
EXC-8166 | TX2406831 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8385 | TX2415500 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8562 | TX2421438 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8046 | TX2402100 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:15 | 0.26 | RESOLVED | 1 | OK
EXC-8549 | TX2420954 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8383 | TX2415461 | FEE_VARIANCE_BREACH | -0.74 | payments-partnerships | 2024-12-11 | 2024-12-17 02:14 | 88.23 | RESOLVED | 120 | OK
EXC-8415 | TX2416722 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8241 | TX2409597 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8597 | TX2422716 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8075 | TX2403463 | ORPHANED_GATEWAY_RECORD | 41.79 | finance-ops-recon | 2024-12-11 | 2024-12-12 12:56 | 26.94 | RESOLVED | 48 | OK
EXC-8428 | TX2417140 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-11 | 2024-12-11 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8478 | TX2418954 | TIMING_MISMATCH_TIMEZONE | -0.01 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8237 | TX2409419 | ORPHANED_GATEWAY_RECORD | 135.66 | finance-ops-recon | 2024-12-12 | 2024-12-12 23:53 | 13.88 | RESOLVED | 48 | OK
EXC-8070 | TX2403258 | FEE_VARIANCE_BREACH | -0.94 | payments-partnerships | 2024-12-12 | 2024-12-12 10:03 | 0.05 | RESOLVED | 120 | OK
EXC-8366 | TX2414442 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8282 | TX2410802 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8040 | TX2401855 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8555 | TX2421255 | FEE_VARIANCE_BREACH | -2.4 | payments-partnerships | 2024-12-12 | 2024-12-18 18:24 | 104.41 | RESOLVED | 120 | OK
EXC-8300 | TX2411569 | FEE_VARIANCE_BREACH | -0.86 | payments-partnerships | 2024-12-12 | 2024-12-18 15:56 | 101.93 | RESOLVED | 120 | OK
EXC-8239 | TX2409526 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:24 | 0.4 | RESOLVED | 1 | OK
EXC-8382 | TX2415367 | ORPHANED_LEDGER_RECORD | -124.91 | revenue-accounting | 2024-12-12 | 2024-12-13 13:57 | 27.95 | RESOLVED | 48 | OK
EXC-8206 | TX2408186 | FEE_VARIANCE_BREACH | -0.76 | payments-partnerships | 2024-12-12 | 2024-12-16 18:23 | 56.39 | RESOLVED | 120 | OK
EXC-8355 | TX2413944 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8457 | TX2418177 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8181 | TX2407300 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8406 | TX2416286 | ORPHANED_GATEWAY_RECORD | 449.08 | finance-ops-recon | 2024-12-12 | 2024-12-13 07:21 | 21.35 | RESOLVED | 48 | OK
EXC-8426 | TX2417101 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8134 | TX2405581 | ORPHANED_LEDGER_RECORD | -278.9 | revenue-accounting | 2024-12-12 | 2024-12-13 12:35 | 26.59 | RESOLVED | 48 | OK
EXC-8657 | TX2425195 | ORPHANED_LEDGER_RECORD | -238.08 | revenue-accounting | 2024-12-12 | 2024-12-13 16:57 | 30.94 | RESOLVED | 48 | OK
EXC-8513 | TX2419744 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-12 | 2024-12-12 15:47 | 5.78 | RESOLVED | 24 | OK
EXC-8143 | TX2405975 | ORPHANED_GATEWAY_RECORD | 109.1 | finance-ops-recon | 2024-12-12 | 2024-12-13 03:02 | 17.03 | RESOLVED | 48 | OK
EXC-8203 | TX2408092 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8200 | TX2407978 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-12 | 2024-12-12 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8453 | TX2417968 | ORPHANED_GATEWAY_RECORD | 1820.14 | finance-ops-recon | 2024-12-12 | 2024-12-12 13:14 | 3.23 | RESOLVED | 48 | OK
EXC-8423 | TX2417046 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8135 | TX2405587 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8326 | TX2412806 | ORPHANED_LEDGER_RECORD | -42.01 | revenue-accounting | 2024-12-13 | 2024-12-19 20:19 | 106.32 | RESOLVED | 48 | BREACH
EXC-8337 | TX2413218 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-13 | 2024-12-16 21:57 | 35.95 | RESOLVED | 24 | BREACH
EXC-8164 | TX2406796 | FEE_VARIANCE_BREACH | -0.65 | payments-partnerships | 2024-12-13 | 2024-12-18 09:19 | 71.31 | RESOLVED | 120 | OK
EXC-8494 | TX2419197 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:06 | 0.11 | RESOLVED | 1 | OK
EXC-8016 | TX2400817 | ORPHANED_GATEWAY_RECORD | 641.43 | finance-ops-recon | 2024-12-13 | 2024-12-16 20:48 | 34.8 | RESOLVED | 48 | OK
EXC-8638 | TX2424276 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8133 | TX2405531 | ORPHANED_GATEWAY_RECORD | 146.47 | finance-ops-recon | 2024-12-13 | 2024-12-16 12:12 | 26.2 | RESOLVED | 48 | OK
EXC-8234 | TX2409217 | FEE_VARIANCE_BREACH | -0.64 | payments-partnerships | 2024-12-13 | 2024-12-16 12:16 | 26.27 | RESOLVED | 120 | OK
EXC-8464 | TX2418469 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8553 | TX2421147 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8264 | TX2410199 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-13 | 2024-12-13 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8527 | TX2420021 | FEE_VARIANCE_BREACH | -1.04 | payments-partnerships | 2024-12-13 | 2024-12-23 00:59 | 134.98 | RESOLVED | 120 | BREACH
EXC-8505 | TX2419518 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-13 | 2024-12-17 10:04 | 48.06 | RESOLVED | 24 | BREACH
EXC-8130 | TX2405419 | ORPHANED_LEDGER_RECORD | -207.5 | revenue-accounting | 2024-12-13 | 2024-12-17 11:18 | 49.3 | RESOLVED | 48 | BREACH
EXC-8010 | TX2400507 | ORPHANED_GATEWAY_RECORD | 111.21 | finance-ops-recon | 2024-12-13 | 2024-12-16 21:23 | 35.38 | RESOLVED | 48 | OK
EXC-8528 | TX2420028 | ORPHANED_GATEWAY_RECORD | 632.65 | finance-ops-recon | 2024-12-16 | 2024-12-18 05:20 | 43.33 | RESOLVED | 48 | OK
EXC-8566 | TX2421724 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8373 | TX2414713 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8531 | TX2420148 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8048 | TX2402215 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8507 | TX2419574 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8521 | TX2419881 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8275 | TX2410528 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8283 | TX2410841 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8313 | TX2412104 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8561 | TX2421400 | FEE_VARIANCE_BREACH | -0.56 | payments-partnerships | 2024-12-16 | 2024-12-18 05:50 | 43.83 | RESOLVED | 120 | OK
EXC-8498 | TX2419365 | FEE_VARIANCE_BREACH | -1.28 | payments-partnerships | 2024-12-16 | 2024-12-23 01:51 | 111.86 | RESOLVED | 120 | OK
EXC-8042 | TX2402016 | ORPHANED_LEDGER_RECORD | -95.05 | revenue-accounting | 2024-12-16 | 2024-12-19 20:51 | 82.85 | RESOLVED | 48 | BREACH
EXC-8551 | TX2421106 | ORPHANED_GATEWAY_RECORD | 769.84 | finance-ops-recon | 2024-12-16 | 2024-12-17 01:09 | 15.14 | RESOLVED | 48 | OK
EXC-8363 | TX2414284 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8087 | TX2403886 | ORPHANED_GATEWAY_RECORD | 669.96 | finance-ops-recon | 2024-12-16 | 2024-12-18 12:40 | 50.66 | RESOLVED | 48 | BREACH
EXC-8361 | TX2414242 | UNCLASSIFIED_VARIANCE | -45 | recon-lead | 2024-12-16 | 2024-12-17 11:29 | 25.48 | RESOLVED | 24 | BREACH
EXC-8554 | TX2421153 | FEE_VARIANCE_BREACH | -3.88 | payments-partnerships | 2024-12-16 | 2024-12-19 04:50 | 66.83 | RESOLVED | 120 | OK
EXC-8329 | TX2412883 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8321 | TX2412610 | FEE_VARIANCE_BREACH | -1.69 | payments-partnerships | 2024-12-16 | 2024-12-20 07:54 | 93.89 | RESOLVED | 120 | OK
EXC-8089 | TX2403917 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8039 | TX2401806 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8091 | TX2404057 | ORPHANED_GATEWAY_RECORD | 37.18 | finance-ops-recon | 2024-12-16 | 2024-12-16 13:02 | 3.03 | RESOLVED | 48 | OK
EXC-8323 | TX2412653 | FEE_VARIANCE_BREACH | -0.93 | payments-partnerships | 2024-12-16 | 2024-12-19 18:41 | 80.68 | RESOLVED | 120 | OK
EXC-8293 | TX2411179 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8078 | TX2403572 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8559 | TX2421380 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8079 | TX2403622 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-16 | 2024-12-17 20:54 | 34.9 | RESOLVED | 24 | BREACH
EXC-8497 | TX2419265 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8290 | TX2411117 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8096 | TX2404497 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8220 | TX2408855 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8401 | TX2416145 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8620 | TX2423320 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8272 | TX2410438 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8627 | TX2423685 | FEE_VARIANCE_BREACH | -3.14 | payments-partnerships | 2024-12-16 | 2024-12-19 22:30 | 84.49 | RESOLVED | 120 | OK
EXC-8629 | TX2423832 | FEE_VARIANCE_BREACH | -1.39 | payments-partnerships | 2024-12-16 | 2024-12-20 18:35 | 104.59 | RESOLVED | 120 | OK
EXC-8459 | TX2418344 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8636 | TX2424059 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8189 | TX2407699 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8188 | TX2407599 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8185 | TX2407389 | ORPHANED_LEDGER_RECORD | -195.85 | revenue-accounting | 2024-12-16 | 2024-12-19 05:48 | 67.8 | RESOLVED | 48 | BREACH
EXC-8418 | TX2416838 | ORPHANED_GATEWAY_RECORD | 980.19 | finance-ops-recon | 2024-12-16 | 2024-12-19 07:25 | 69.42 | RESOLVED | 48 | BREACH
EXC-8480 | TX2418978 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8178 | TX2407177 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8421 | TX2416961 | FEE_VARIANCE_BREACH | -1.24 | payments-partnerships | 2024-12-16 | 2024-12-19 17:46 | 79.77 | RESOLVED | 120 | OK
EXC-8456 | TX2418165 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8012 | TX2400555 | ORPHANED_LEDGER_RECORD | -446.6 | revenue-accounting | 2024-12-16 | 2024-12-19 09:59 | 71.98 | RESOLVED | 48 | BREACH
EXC-8009 | TX2400465 | FEE_VARIANCE_BREACH | -2.3 | payments-partnerships | 2024-12-16 | 2024-12-23 07:09 | 117.16 | RESOLVED | 120 | OK
EXC-8061 | TX2402823 | FEE_VARIANCE_BREACH | -8.26 | payments-partnerships | 2024-12-16 | 2024-12-18 07:03 | 45.05 | RESOLVED | 120 | OK
EXC-8429 | TX2417145 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8430 | TX2417146 | ORPHANED_LEDGER_RECORD | -52.36 | revenue-accounting | 2024-12-16 | 2024-12-19 07:54 | 69.9 | RESOLVED | 48 | BREACH
EXC-8451 | TX2417909 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8449 | TX2417831 | ORPHANED_GATEWAY_RECORD | 110.7 | finance-ops-recon | 2024-12-16 | 2024-12-17 10:42 | 24.7 | RESOLVED | 48 | OK
EXC-8436 | TX2417360 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8669 | TX2425565 | ORPHANED_LEDGER_RECORD | -54.24 | revenue-accounting | 2024-12-16 | 2024-12-19 09:41 | 71.68 | RESOLVED | 48 | BREACH
EXC-8057 | TX2402716 | ORPHANED_LEDGER_RECORD | -902.26 | revenue-accounting | 2024-12-16 | 2024-12-17 23:17 | 37.28 | RESOLVED | 48 | OK
EXC-8171 | TX2406882 | ORPHANED_GATEWAY_RECORD | 494.48 | finance-ops-recon | 2024-12-16 | 2024-12-18 00:55 | 38.92 | RESOLVED | 48 | OK
EXC-8487 | TX2419062 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8215 | TX2408615 | ORPHANED_LEDGER_RECORD | -95.54 | revenue-accounting | 2024-12-16 | 2024-12-18 14:08 | 52.13 | RESOLVED | 48 | BREACH
EXC-8524 | TX2419989 | FEE_VARIANCE_BREACH | -1.81 | payments-partnerships | 2024-12-16 | 2024-12-24 18:35 | 152.59 | RESOLVED | 120 | BREACH
EXC-8249 | TX2409748 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8393 | TX2415866 | ORPHANED_GATEWAY_RECORD | 226.32 | finance-ops-recon | 2024-12-16 | 2024-12-17 13:17 | 27.28 | RESOLVED | 48 | OK
EXC-8381 | TX2415261 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8588 | TX2422444 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8595 | TX2422681 | FEE_VARIANCE_BREACH | -1.08 | payments-partnerships | 2024-12-16 | 2024-12-19 08:41 | 70.68 | RESOLVED | 120 | OK
EXC-8240 | TX2409529 | ORPHANED_GATEWAY_RECORD | 1643.49 | finance-ops-recon | 2024-12-16 | 2024-12-17 05:42 | 19.71 | RESOLVED | 48 | OK
EXC-8496 | TX2419232 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:24 | 0.4 | RESOLVED | 1 | OK
EXC-8261 | TX2410117 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:15 | 0.26 | RESOLVED | 1 | OK
EXC-8578 | TX2421869 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8262 | TX2410151 | ORPHANED_GATEWAY_RECORD | 397.49 | finance-ops-recon | 2024-12-16 | 2024-12-17 22:52 | 36.86 | RESOLVED | 48 | OK
EXC-8391 | TX2415772 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8034 | TX2401633 | FEE_VARIANCE_BREACH | -1.9 | payments-partnerships | 2024-12-16 | 2024-12-19 17:13 | 79.21 | RESOLVED | 120 | OK
EXC-8115 | TX2404982 | ORPHANED_LEDGER_RECORD | -753.38 | revenue-accounting | 2024-12-16 | 2024-12-18 20:23 | 58.39 | RESOLVED | 48 | BREACH
EXC-8116 | TX2405026 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8488 | TX2419094 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:15 | 0.24 | RESOLVED | 1 | OK
EXC-8023 | TX2401328 | ORPHANED_GATEWAY_RECORD | 114.03 | finance-ops-recon | 2024-12-16 | 2024-12-16 19:50 | 9.83 | RESOLVED | 48 | OK
EXC-8227 | TX2409053 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:26 | 0.43 | RESOLVED | 1 | OK
EXC-8114 | TX2404951 | FEE_VARIANCE_BREACH | -0.75 | payments-partnerships | 2024-12-16 | 2024-12-19 21:34 | 83.56 | RESOLVED | 120 | OK
EXC-8110 | TX2404836 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-16 | 2024-12-16 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8535 | TX2420344 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8433 | TX2417295 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:24 | 0.4 | RESOLVED | 1 | OK
EXC-8576 | TX2421857 | FEE_VARIANCE_BREACH | -2.95 | payments-partnerships | 2024-12-17 | 2024-12-20 04:55 | 66.92 | RESOLVED | 120 | OK
EXC-8270 | TX2410360 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:20 | 0.34 | RESOLVED | 1 | OK
EXC-8380 | TX2415066 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8107 | TX2404797 | FEE_VARIANCE_BREACH | -0.64 | payments-partnerships | 2024-12-17 | 2024-12-23 16:38 | 102.64 | RESOLVED | 120 | OK
EXC-8304 | TX2411726 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:25 | 0.41 | RESOLVED | 1 | OK
EXC-8642 | TX2424457 | ORPHANED_LEDGER_RECORD | -1164.51 | revenue-accounting | 2024-12-17 | 2024-12-18 20:30 | 34.49 | RESOLVED | 48 | OK
EXC-8622 | TX2423477 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:06 | 0.11 | RESOLVED | 1 | OK
EXC-8204 | TX2408166 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8126 | TX2405281 | FEE_VARIANCE_BREACH | -9.98 | payments-partnerships | 2024-12-17 | 2024-12-19 16:55 | 54.91 | RESOLVED | 120 | OK
EXC-8172 | TX2406926 | ORPHANED_GATEWAY_RECORD | 151.46 | finance-ops-recon | 2024-12-17 | 2024-12-18 22:50 | 36.84 | RESOLVED | 48 | OK
EXC-8294 | TX2411218 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8196 | TX2407857 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8327 | TX2412819 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-17 | 2024-12-17 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8635 | TX2424037 | ORPHANED_GATEWAY_RECORD | 206.27 | finance-ops-recon | 2024-12-17 | 2024-12-19 01:22 | 39.36 | RESOLVED | 48 | OK
EXC-8386 | TX2415568 | FEE_VARIANCE_BREACH | -0.82 | payments-partnerships | 2024-12-17 | 2024-12-20 18:20 | 80.34 | RESOLVED | 120 | OK
EXC-8369 | TX2414558 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8388 | TX2415731 | ORPHANED_GATEWAY_RECORD | 148.19 | finance-ops-recon | 2024-12-18 | 2024-12-19 00:23 | 14.38 | RESOLVED | 48 | OK
EXC-8509 | TX2419680 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8420 | TX2416959 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8053 | TX2402531 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:09 | 0.16 | RESOLVED | 1 | OK
EXC-8073 | TX2403390 | ORPHANED_LEDGER_RECORD | -356.99 | revenue-accounting | 2024-12-18 | 2024-12-20 18:49 | 56.82 | RESOLVED | 48 | BREACH
EXC-8471 | TX2418698 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8059 | TX2402770 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8120 | TX2405141 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8084 | TX2403773 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8246 | TX2409666 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8585 | TX2422388 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8569 | TX2421746 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8187 | TX2407486 | ORPHANED_LEDGER_RECORD | -94.43 | revenue-accounting | 2024-12-18 | 2024-12-23 11:57 | 73.94 | RESOLVED | 48 | BREACH
EXC-8571 | TX2421751 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8165 | TX2406827 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:22 | 0.36 | RESOLVED | 1 | OK
EXC-8616 | TX2423232 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8011 | TX2400511 | ORPHANED_LEDGER_RECORD | -385.84 | revenue-accounting | 2024-12-18 | 2024-12-20 01:09 | 39.15 | RESOLVED | 48 | OK
EXC-8155 | TX2406323 | ORPHANED_LEDGER_RECORD | -347.11 | revenue-accounting | 2024-12-18 | 2024-12-23 05:03 | 67.05 | RESOLVED | 48 | BREACH
EXC-8678 | TX2425939 | FEE_VARIANCE_BREACH | -2.63 | payments-partnerships | 2024-12-18 | 2024-12-23 22:43 | 84.72 | RESOLVED | 120 | OK
EXC-8152 | TX2406249 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.06 | RESOLVED | 1 | OK
EXC-8005 | TX2400243 | FEE_VARIANCE_BREACH | -1.18 | payments-partnerships | 2024-12-18 | 2024-12-20 07:10 | 45.16 | RESOLVED | 120 | OK
EXC-8003 | TX2400102 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8526 | TX2420005 | FEE_VARIANCE_BREACH | -5.44 | payments-partnerships | 2024-12-18 | 2024-12-24 00:45 | 86.75 | RESOLVED | 120 | OK
EXC-8345 | TX2413621 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8332 | TX2412957 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8280 | TX2410755 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-18 | 2024-12-18 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8250 | TX2409800 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-19 | 2024-12-23 08:16 | 46.26 | RESOLVED | 24 | BREACH
EXC-8493 | TX2419182 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:06 | 0.11 | RESOLVED | 1 | OK
EXC-8127 | TX2405332 | ORPHANED_LEDGER_RECORD | -121.62 | revenue-accounting | 2024-12-19 | 2024-12-19 18:35 | 8.58 | RESOLVED | 48 | OK
EXC-8020 | TX2401270 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8217 | TX2408776 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:04 | 0.07 | RESOLVED | 1 | OK
EXC-8214 | TX2408539 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8632 | TX2423946 | FEE_VARIANCE_BREACH | -8.8 | payments-partnerships | 2024-12-19 | 2024-12-25 03:54 | 89.9 | RESOLVED | 120 | OK
EXC-8193 | TX2407798 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:22 | 0.36 | RESOLVED | 1 | OK
EXC-8179 | TX2407180 | FEE_VARIANCE_BREACH | -6.08 | payments-partnerships | 2024-12-19 | 2024-12-25 17:23 | 103.38 | RESOLVED | 120 | OK
EXC-8659 | TX2425203 | FEE_VARIANCE_BREACH | -2.11 | payments-partnerships | 2024-12-19 | 2024-12-23 15:47 | 53.78 | RESOLVED | 120 | OK
EXC-8219 | TX2408813 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8105 | TX2404789 | ORPHANED_LEDGER_RECORD | -266.88 | revenue-accounting | 2024-12-19 | 2024-12-23 05:40 | 43.66 | RESOLVED | 48 | OK
EXC-8349 | TX2413784 | FEE_VARIANCE_BREACH | -3.73 | payments-partnerships | 2024-12-19 | 2024-12-23 01:47 | 39.78 | RESOLVED | 120 | OK
EXC-8289 | TX2411104 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8342 | TX2413568 | FEE_VARIANCE_BREACH | -1.66 | payments-partnerships | 2024-12-19 | 2024-12-25 22:00 | 108 | RESOLVED | 120 | OK
EXC-8557 | TX2421347 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:18 | 0.31 | RESOLVED | 1 | OK
EXC-8572 | TX2421786 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8379 | TX2415041 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8043 | TX2402065 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-19 | 2024-12-19 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8064 | TX2402909 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-20 | 2024-12-24 19:04 | 57.07 | RESOLVED | 24 | BREACH
EXC-8510 | TX2419685 | FEE_VARIANCE_BREACH | -1.3 | payments-partnerships | 2024-12-20 | 2024-12-24 03:22 | 41.36 | RESOLVED | 120 | OK
EXC-8129 | TX2405370 | TIMING_MISMATCH_TIMEZONE | -0.01 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:23 | 0.38 | RESOLVED | 1 | OK
EXC-8317 | TX2412354 | FEE_VARIANCE_BREACH | -1.4 | payments-partnerships | 2024-12-20 | 2024-12-26 13:38 | 99.63 | RESOLVED | 120 | OK
EXC-8256 | TX2410043 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8291 | TX2411137 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8514 | TX2419753 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8425 | TX2417082 | ORPHANED_LEDGER_RECORD | -460.9 | revenue-accounting | 2024-12-20 | 2024-12-23 08:15 | 22.26 | RESOLVED | 48 | OK
EXC-8532 | TX2420179 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8340 | TX2413461 | ORPHANED_LEDGER_RECORD | -549.73 | revenue-accounting | 2024-12-20 | 2024-12-23 13:29 | 27.49 | RESOLVED | 48 | OK
EXC-8136 | TX2405669 | FEE_VARIANCE_BREACH | -0.54 | payments-partnerships | 2024-12-20 | 2024-12-26 11:30 | 97.5 | RESOLVED | 120 | OK
EXC-8665 | TX2425475 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8131 | TX2405440 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8541 | TX2420612 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8631 | TX2423892 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8140 | TX2405815 | ORPHANED_GATEWAY_RECORD | 282.83 | finance-ops-recon | 2024-12-20 | 2024-12-24 05:41 | 43.68 | RESOLVED | 48 | OK
EXC-8390 | TX2415750 | FEE_VARIANCE_BREACH | -1.2 | payments-partnerships | 2024-12-20 | 2024-12-27 08:08 | 118.13 | RESOLVED | 120 | OK
EXC-8389 | TX2415735 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8248 | TX2409731 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-20 | 2024-12-20 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8618 | TX2423295 | FEE_VARIANCE_BREACH | -6.21 | payments-partnerships | 2024-12-20 | 2024-12-25 09:09 | 71.15 | RESOLVED | 120 | OK
EXC-8106 | TX2404792 | ORPHANED_GATEWAY_RECORD | 633.7 | finance-ops-recon | 2024-12-20 | 2024-12-23 03:18 | 17.3 | RESOLVED | 48 | OK
EXC-8593 | TX2422530 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8004 | TX2400114 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:24 | 0.4 | RESOLVED | 1 | OK
EXC-8452 | TX2417924 | FEE_VARIANCE_BREACH | -5.5 | payments-partnerships | 2024-12-23 | 2024-12-27 01:32 | 87.54 | RESOLVED | 120 | OK
EXC-8006 | TX2400275 | ORPHANED_GATEWAY_RECORD | 278.05 | finance-ops-recon | 2024-12-23 | 2024-12-23 17:39 | 7.65 | RESOLVED | 48 | OK
EXC-8013 | TX2400566 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8519 | TX2419858 | FEE_VARIANCE_BREACH | -0.75 | payments-partnerships | 2024-12-23 | 2024-12-27 05:37 | 91.61 | RESOLVED | 120 | OK
EXC-8036 | TX2401671 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8658 | TX2425199 | ORPHANED_GATEWAY_RECORD | 906.34 | finance-ops-recon | 2024-12-23 | 2024-12-24 11:08 | 25.13 | RESOLVED | 48 | OK
EXC-8652 | TX2425003 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8594 | TX2422633 | FEE_VARIANCE_BREACH | -0.58 | payments-partnerships | 2024-12-23 | 2024-12-27 06:25 | 92.41 | RESOLVED | 120 | OK
EXC-8045 | TX2402096 | TIMING_MISMATCH_TIMEZONE | 0.01 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8677 | TX2425909 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8520 | TX2419872 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8502 | TX2419407 | TIMING_MISMATCH_TIMEZONE | -0.36 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8479 | TX2418969 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:13 | 0.21 | RESOLVED | 1 | OK
EXC-8640 | TX2424423 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8567 | TX2421734 | FEE_VARIANCE_BREACH | -1.49 | payments-partnerships | 2024-12-23 | 2024-12-26 11:29 | 73.48 | RESOLVED | 120 | OK
EXC-8614 | TX2423225 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8483 | TX2419025 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8621 | TX2423439 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:06 | 0.09 | RESOLVED | 1 | OK
EXC-8052 | TX2402430 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8469 | TX2418635 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8625 | TX2423607 | ORPHANED_GATEWAY_RECORD | 330.43 | finance-ops-recon | 2024-12-23 | 2024-12-24 09:44 | 23.74 | RESOLVED | 48 | OK
EXC-8486 | TX2419051 | ORPHANED_GATEWAY_RECORD | 68.25 | finance-ops-recon | 2024-12-23 | 2024-12-24 16:12 | 30.19 | RESOLVED | 48 | OK
EXC-8525 | TX2420001 | FEE_VARIANCE_BREACH | -0.7 | payments-partnerships | 2024-12-23 | 2024-12-30 14:25 | 124.41 | RESOLVED | 120 | BREACH
EXC-8018 | TX2401139 | FEE_VARIANCE_BREACH | -5.27 | payments-partnerships | 2024-12-23 | 2024-12-26 01:36 | 63.6 | RESOLVED | 120 | OK
EXC-8512 | TX2419725 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8044 | TX2402081 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8611 | TX2423149 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8024 | TX2401365 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8604 | TX2422931 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8641 | TX2424449 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8644 | TX2424492 | FEE_VARIANCE_BREACH | -0.91 | payments-partnerships | 2024-12-23 | 2024-12-26 12:06 | 74.1 | RESOLVED | 120 | OK
EXC-8409 | TX2416513 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8265 | TX2410202 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8177 | TX2407176 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8438 | TX2417385 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8168 | TX2406868 | ORPHANED_LEDGER_RECORD | -216.39 | revenue-accounting | 2024-12-23 | 2024-12-24 12:21 | 26.35 | RESOLVED | 48 | OK
EXC-8299 | TX2411519 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8301 | TX2411621 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8213 | TX2408459 | ORPHANED_GATEWAY_RECORD | 316.58 | finance-ops-recon | 2024-12-23 | 2024-12-24 00:09 | 14.15 | RESOLVED | 48 | OK
EXC-8394 | TX2415938 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.16 | RESOLVED | 1 | OK
EXC-8067 | TX2402999 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:06 | 0.09 | RESOLVED | 1 | OK
EXC-8157 | TX2406427 | FEE_VARIANCE_BREACH | -1.23 | payments-partnerships | 2024-12-23 | 2024-12-26 22:37 | 84.61 | RESOLVED | 120 | OK
EXC-8160 | TX2406607 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8377 | TX2414817 | FEE_VARIANCE_BREACH | -0.92 | payments-partnerships | 2024-12-23 | 2024-12-26 17:11 | 79.18 | RESOLVED | 120 | OK
EXC-8192 | TX2407788 | FEE_VARIANCE_BREACH | -1.54 | payments-partnerships | 2024-12-23 | 2024-12-27 11:44 | 97.73 | RESOLVED | 120 | OK
EXC-8068 | TX2403009 | ORPHANED_GATEWAY_RECORD | 136.75 | finance-ops-recon | 2024-12-23 | 2024-12-24 12:11 | 26.19 | RESOLVED | 48 | OK
EXC-8310 | TX2411971 | FEE_VARIANCE_BREACH | -1.13 | payments-partnerships | 2024-12-23 | 2024-12-27 16:01 | 102.01 | RESOLVED | 120 | OK
EXC-8162 | TX2406733 | ORPHANED_GATEWAY_RECORD | 200.31 | finance-ops-recon | 2024-12-23 | 2024-12-25 03:32 | 41.53 | RESOLVED | 48 | OK
EXC-8314 | TX2412124 | FEE_VARIANCE_BREACH | -0.69 | payments-partnerships | 2024-12-23 | 2024-12-26 21:53 | 83.89 | RESOLVED | 120 | OK
EXC-8132 | TX2405452 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:28 | 0.47 | RESOLVED | 1 | OK
EXC-8360 | TX2414203 | ORPHANED_GATEWAY_RECORD | 180.73 | finance-ops-recon | 2024-12-23 | 2024-12-24 15:19 | 29.32 | RESOLVED | 48 | OK
EXC-8082 | TX2403739 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8081 | TX2403659 | FEE_VARIANCE_BREACH | -0.83 | payments-partnerships | 2024-12-23 | 2024-12-25 19:13 | 57.21 | RESOLVED | 120 | OK
EXC-8319 | TX2412491 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8077 | TX2403515 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8346 | TX2413640 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8244 | TX2409644 | ORPHANED_GATEWAY_RECORD | 1297.96 | finance-ops-recon | 2024-12-23 | 2024-12-24 17:10 | 31.17 | RESOLVED | 48 | OK
EXC-8184 | TX2407369 | ORPHANED_GATEWAY_RECORD | 1737.24 | finance-ops-recon | 2024-12-23 | 2024-12-25 21:24 | 59.4 | RESOLVED | 48 | BREACH
EXC-8402 | TX2416165 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8154 | TX2406320 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-23 | 2024-12-24 17:41 | 31.68 | RESOLVED | 24 | BREACH
EXC-8273 | TX2410460 | FEE_VARIANCE_BREACH | -6.74 | payments-partnerships | 2024-12-23 | 2024-12-30 04:36 | 114.6 | RESOLVED | 120 | OK
EXC-8263 | TX2410175 | FEE_VARIANCE_BREACH | -1.08 | payments-partnerships | 2024-12-23 | 2024-12-26 15:28 | 77.46 | RESOLVED | 120 | OK
EXC-8099 | TX2404587 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8098 | TX2404574 | ORPHANED_LEDGER_RECORD | -120.02 | revenue-accounting | 2024-12-23 | 2024-12-24 07:01 | 21.02 | RESOLVED | 48 | OK
EXC-8274 | TX2410500 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8063 | TX2402874 | FEE_VARIANCE_BREACH | -2.77 | payments-partnerships | 2024-12-23 | 2024-12-27 19:42 | 105.7 | RESOLVED | 120 | OK
EXC-8224 | TX2408988 | FEE_VARIANCE_BREACH | -1.51 | payments-partnerships | 2024-12-23 | 2024-12-26 00:48 | 62.8 | RESOLVED | 120 | OK
EXC-8412 | TX2416648 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8410 | TX2416534 | UNCLASSIFIED_VARIANCE | -45 | recon-lead | 2024-12-23 | 2024-12-24 11:14 | 25.24 | RESOLVED | 24 | BREACH
EXC-8338 | TX2413276 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-23 | 2024-12-23 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8094 | TX2404339 | ORPHANED_GATEWAY_RECORD | 379.56 | finance-ops-recon | 2024-12-23 | 2024-12-25 03:08 | 41.13 | RESOLVED | 48 | OK
EXC-8183 | TX2407350 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8341 | TX2413507 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8347 | TX2413696 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:30 | 0.49 | RESOLVED | 1 | OK
EXC-8218 | TX2408779 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8448 | TX2417816 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:09 | 0.16 | RESOLVED | 1 | OK
EXC-8362 | TX2414262 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8450 | TX2417867 | FEE_VARIANCE_BREACH | -1.13 | payments-partnerships | 2024-12-24 | 2024-12-31 00:33 | 110.55 | RESOLVED | 120 | OK
EXC-8083 | TX2403746 | FEE_VARIANCE_BREACH | -2.56 | payments-partnerships | 2024-12-24 | 2024-12-31 11:44 | 121.73 | RESOLVED | 120 | BREACH
EXC-8026 | TX2401382 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8161 | TX2406651 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8503 | TX2419473 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8374 | TX2414773 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8473 | TX2418791 | FEE_VARIANCE_BREACH | -2.55 | payments-partnerships | 2024-12-24 | 2024-12-26 21:59 | 59.98 | RESOLVED | 120 | OK
EXC-8654 | TX2425123 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8422 | TX2417041 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8146 | TX2406037 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8151 | TX2406236 | FEE_VARIANCE_BREACH | -0.8 | payments-partnerships | 2024-12-24 | 2024-12-30 01:57 | 87.95 | RESOLVED | 120 | OK
EXC-8558 | TX2421376 | FEE_VARIANCE_BREACH | -0.6 | payments-partnerships | 2024-12-24 | 2024-12-30 07:42 | 93.7 | RESOLVED | 120 | OK
EXC-8637 | TX2424086 | FEE_VARIANCE_BREACH | -0.87 | payments-partnerships | 2024-12-24 | 2024-12-27 15:12 | 77.19 | RESOLVED | 120 | OK
EXC-8492 | TX2419175 | ORPHANED_LEDGER_RECORD | -165.52 | revenue-accounting | 2024-12-24 | 2024-12-27 04:33 | 66.55 | RESOLVED | 48 | BREACH
EXC-8467 | TX2418616 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8278 | TX2410620 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8088 | TX2403893 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-24 | 2024-12-24 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8515 | TX2419773 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8147 | TX2406054 | UNCLASSIFIED_VARIANCE | -7.49 | recon-lead | 2024-12-25 | 2024-12-25 20:07 | 10.11 | RESOLVED | 24 | OK
EXC-8447 | TX2417735 | FEE_VARIANCE_BREACH | -1.72 | payments-partnerships | 2024-12-25 | 2024-12-31 08:01 | 94.01 | RESOLVED | 120 | OK
EXC-8612 | TX2423166 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8461 | TX2418406 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8125 | TX2405260 | FEE_VARIANCE_BREACH | -1.69 | payments-partnerships | 2024-12-25 | 2025-01-01 12:48 | 122.8 | RESOLVED | 120 | BREACH
EXC-8443 | TX2417644 | ORPHANED_LEDGER_RECORD | -342 | revenue-accounting | 2024-12-25 | 2024-12-30 15:36 | 77.6 | RESOLVED | 48 | BREACH
EXC-8533 | TX2420227 | FEE_VARIANCE_BREACH | -3.8 | payments-partnerships | 2024-12-25 | 2025-01-01 19:21 | 129.36 | RESOLVED | 120 | BREACH
EXC-8523 | TX2419988 | ORPHANED_LEDGER_RECORD | -201.73 | revenue-accounting | 2024-12-25 | 2024-12-26 11:13 | 25.22 | RESOLVED | 48 | OK
EXC-8645 | TX2424533 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8231 | TX2409119 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:21 | 0.34 | RESOLVED | 1 | OK
EXC-8586 | TX2422434 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8245 | TX2409651 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8489 | TX2419105 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8311 | TX2411991 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8306 | TX2411806 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8030 | TX2401449 | FEE_VARIANCE_BREACH | -10.33 | payments-partnerships | 2024-12-25 | 2024-12-30 15:22 | 77.36 | RESOLVED | 120 | OK
EXC-8589 | TX2422448 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-25 | 2024-12-25 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8378 | TX2414975 | FEE_VARIANCE_BREACH | -0.52 | payments-partnerships | 2024-12-25 | 2024-12-30 14:54 | 76.9 | RESOLVED | 120 | OK
EXC-8100 | TX2404588 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8104 | TX2404694 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8080 | TX2403625 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8328 | TX2412852 | ORPHANED_LEDGER_RECORD | -311.19 | revenue-accounting | 2024-12-26 | 2024-12-30 08:14 | 46.23 | RESOLVED | 48 | OK
EXC-8537 | TX2420372 | FEE_VARIANCE_BREACH | -3.48 | payments-partnerships | 2024-12-26 | 2025-01-01 15:40 | 101.67 | RESOLVED | 120 | OK
EXC-8032 | TX2401574 | FEE_VARIANCE_BREACH | -0.72 | payments-partnerships | 2024-12-26 | 2024-12-30 22:57 | 60.94 | RESOLVED | 120 | OK
EXC-8180 | TX2407290 | ORPHANED_LEDGER_RECORD | -62.71 | revenue-accounting | 2024-12-26 | 2024-12-27 09:12 | 23.19 | RESOLVED | 48 | OK
EXC-8170 | TX2406875 | FEE_VARIANCE_BREACH | -0.53 | payments-partnerships | 2024-12-26 | 2024-12-31 16:02 | 78.04 | RESOLVED | 120 | OK
EXC-8364 | TX2414309 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8370 | TX2414570 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8662 | TX2425321 | ORPHANED_GATEWAY_RECORD | 749.22 | finance-ops-recon | 2024-12-26 | 2024-12-27 14:07 | 28.12 | RESOLVED | 48 | OK
EXC-8153 | TX2406253 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8128 | TX2405359 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8490 | TX2419107 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8387 | TX2415600 | ORPHANED_LEDGER_RECORD | -187.68 | revenue-accounting | 2024-12-26 | 2024-12-30 06:10 | 44.16 | RESOLVED | 48 | OK
EXC-8113 | TX2404943 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8504 | TX2419497 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8408 | TX2416416 | FEE_VARIANCE_BREACH | -2.2 | payments-partnerships | 2024-12-26 | 2024-12-30 00:27 | 38.45 | RESOLVED | 120 | OK
EXC-8336 | TX2413194 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8201 | TX2407989 | FEE_VARIANCE_BREACH | -0.65 | payments-partnerships | 2024-12-26 | 2024-12-30 19:53 | 57.88 | RESOLVED | 120 | OK
EXC-8400 | TX2416127 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8145 | TX2406020 | UNCLASSIFIED_VARIANCE | -12 | recon-lead | 2024-12-26 | 2024-12-30 05:04 | 43.07 | RESOLVED | 24 | BREACH
EXC-8675 | TX2425715 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:20 | 0.34 | RESOLVED | 1 | OK
EXC-8353 | TX2413903 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8348 | TX2413736 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-26 | 2024-12-26 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8141 | TX2405824 | FEE_VARIANCE_BREACH | -1.42 | payments-partnerships | 2024-12-26 | 2025-01-03 15:46 | 149.76 | RESOLVED | 120 | BREACH
EXC-8671 | TX2425610 | ORPHANED_LEDGER_RECORD | -474.35 | revenue-accounting | 2024-12-26 | 2024-12-30 15:01 | 53.02 | RESOLVED | 48 | BREACH
EXC-8022 | TX2401326 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8138 | TX2405769 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:18 | 0.29 | RESOLVED | 1 | OK
EXC-8284 | TX2410847 | FEE_VARIANCE_BREACH | -0.63 | payments-partnerships | 2024-12-27 | 2025-01-02 10:40 | 96.66 | RESOLVED | 120 | OK
EXC-8574 | TX2421831 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8060 | TX2402817 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:16 | 0.26 | RESOLVED | 1 | OK
EXC-8577 | TX2421858 | ORPHANED_GATEWAY_RECORD | 567.33 | finance-ops-recon | 2024-12-27 | 2024-12-31 00:41 | 38.68 | RESOLVED | 48 | OK
EXC-8668 | TX2425562 | FEE_VARIANCE_BREACH | -6.21 | payments-partnerships | 2024-12-27 | 2025-01-01 18:43 | 80.72 | RESOLVED | 120 | OK
EXC-8435 | TX2417318 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8529 | TX2420122 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8295 | TX2411242 | FEE_VARIANCE_BREACH | -7.76 | payments-partnerships | 2024-12-27 | 2024-12-31 05:13 | 43.22 | RESOLVED | 120 | OK
EXC-8302 | TX2411648 | FEE_VARIANCE_BREACH | -1.44 | payments-partnerships | 2024-12-27 | 2025-01-01 15:55 | 77.91 | RESOLVED | 120 | OK
EXC-8343 | TX2413603 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8312 | TX2411993 | ORPHANED_GATEWAY_RECORD | 37.84 | finance-ops-recon | 2024-12-27 | 2024-12-30 21:52 | 35.87 | RESOLVED | 48 | OK
EXC-8163 | TX2406781 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8536 | TX2420355 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:10 | 0.17 | RESOLVED | 1 | OK
EXC-8350 | TX2413785 | FEE_VARIANCE_BREACH | -1.16 | payments-partnerships | 2024-12-27 | 2024-12-31 19:28 | 57.46 | RESOLVED | 120 | OK
EXC-8356 | TX2413959 | ORPHANED_GATEWAY_RECORD | 414 | finance-ops-recon | 2024-12-27 | 2024-12-31 08:35 | 46.58 | RESOLVED | 48 | OK
EXC-8517 | TX2419807 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:20 | 0.34 | RESOLVED | 1 | OK
EXC-8518 | TX2419834 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-27 | 2024-12-27 10:19 | 0.32 | RESOLVED | 1 | OK
EXC-8605 | TX2422934 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:18 | 0.3 | RESOLVED | 1 | OK
EXC-8121 | TX2405161 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8617 | TX2423241 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8259 | TX2410091 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:05 | 0.08 | RESOLVED | 1 | OK
EXC-8223 | TX2408960 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:22 | 0.37 | RESOLVED | 1 | OK
EXC-8028 | TX2401432 | FEE_VARIANCE_BREACH | -2.59 | payments-partnerships | 2024-12-30 | 2025-01-03 17:03 | 103.06 | RESOLVED | 120 | OK
EXC-8243 | TX2409629 | FEE_VARIANCE_BREACH | -1.17 | payments-partnerships | 2024-12-30 | 2025-01-03 10:23 | 96.39 | RESOLVED | 120 | OK
EXC-8598 | TX2422721 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8600 | TX2422753 | FEE_VARIANCE_BREACH | -2.81 | payments-partnerships | 2024-12-30 | 2025-01-02 16:00 | 78 | RESOLVED | 120 | OK
EXC-8029 | TX2401436 | FEE_VARIANCE_BREACH | -2.28 | payments-partnerships | 2024-12-30 | 2025-01-03 18:47 | 104.79 | RESOLVED | 120 | OK
EXC-8195 | TX2407849 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8017 | TX2400982 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8607 | TX2423003 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8334 | TX2413128 | FEE_VARIANCE_BREACH | -4.04 | payments-partnerships | 2024-12-30 | 2025-01-01 22:51 | 60.86 | RESOLVED | 120 | OK
EXC-8212 | TX2408435 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8579 | TX2421991 | ORPHANED_GATEWAY_RECORD | 459.57 | finance-ops-recon | 2024-12-30 | 2024-12-31 09:59 | 23.99 | RESOLVED | 48 | OK
EXC-8485 | TX2419043 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:10 | 0.16 | RESOLVED | 1 | OK
EXC-8481 | TX2418993 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:09 | 0.14 | RESOLVED | 1 | OK
EXC-8664 | TX2425427 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8137 | TX2405719 | FEE_VARIANCE_BREACH | -1.16 | payments-partnerships | 2024-12-30 | 2024-12-31 13:23 | 27.38 | RESOLVED | 120 | OK
EXC-8475 | TX2418859 | UNCLASSIFIED_VARIANCE | -7.5 | recon-lead | 2024-12-30 | 2024-12-31 19:26 | 33.43 | RESOLVED | 24 | BREACH
EXC-8474 | TX2418823 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.21 | RESOLVED | 1 | OK
EXC-8472 | TX2418699 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8670 | TX2425566 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8465 | TX2418492 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8462 | TX2418455 | FEE_VARIANCE_BREACH | -2.51 | payments-partnerships | 2024-12-30 | 2025-01-03 20:39 | 106.65 | RESOLVED | 120 | OK
EXC-8673 | TX2425692 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:19 | 0.31 | RESOLVED | 1 | OK
EXC-8142 | TX2405825 | FEE_VARIANCE_BREACH | -1.99 | payments-partnerships | 2024-12-30 | 2025-01-03 15:19 | 101.31 | RESOLVED | 120 | OK
EXC-8432 | TX2417181 | FEE_VARIANCE_BREACH | -2.08 | payments-partnerships | 2024-12-30 | 2025-01-03 02:04 | 88.06 | RESOLVED | 120 | OK
EXC-8446 | TX2417734 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:08 | 0.13 | RESOLVED | 1 | OK
EXC-8444 | TX2417655 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8033 | TX2401623 | FEE_VARIANCE_BREACH | -1.13 | payments-partnerships | 2024-12-30 | 2025-01-03 08:16 | 94.27 | RESOLVED | 120 | OK
EXC-8500 | TX2419368 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8384 | TX2415490 | FEE_VARIANCE_BREACH | -14.03 | payments-partnerships | 2024-12-30 |  |  | OPEN | 120
EXC-8069 | TX2403089 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8277 | TX2410581 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:18 | 0.31 | RESOLVED | 1 | OK
EXC-8169 | TX2406871 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:14 | 0.24 | RESOLVED | 1 | OK
EXC-8564 | TX2421474 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8286 | TX2410921 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-30 | 2025-01-01 02:48 | 40.8 | RESOLVED | 24 | BREACH
EXC-8288 | TX2411063 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:13 | 0.21 | RESOLVED | 1 | OK
EXC-8375 | TX2414798 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:15 | 0.26 | RESOLVED | 1 | OK
EXC-8547 | TX2420806 | FEE_VARIANCE_BREACH | -0.74 | payments-partnerships | 2024-12-30 | 2025-01-02 12:00 | 74 | RESOLVED | 120 | OK
EXC-8092 | TX2404097 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8544 | TX2420734 | FEE_VARIANCE_BREACH | -2.37 | payments-partnerships | 2024-12-30 | 2025-01-02 21:28 | 83.47 | RESOLVED | 120 | OK
EXC-8534 | TX2420319 | ORPHANED_GATEWAY_RECORD | 53.17 | finance-ops-recon | 2024-12-30 | 2025-01-01 08:27 | 46.45 | RESOLVED | 48 | OK
EXC-8358 | TX2414106 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8365 | TX2414421 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:07 | 0.11 | RESOLVED | 1 | OK
EXC-8651 | TX2424931 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8371 | TX2414648 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-30 | 2024-12-30 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8649 | TX2424727 | FEE_VARIANCE_BREACH | -1.02 | payments-partnerships | 2024-12-30 | 2025-01-02 16:52 | 78.87 | RESOLVED | 120 | OK
EXC-8205 | TX2408184 | ORPHANED_GATEWAY_RECORD | 184.74 | finance-ops-recon | 2024-12-31 | 2025-01-02 03:09 | 41.16 | RESOLVED | 48 | OK
EXC-8001 | TX2400018 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:15 | 0.24 | RESOLVED | 1 | OK
EXC-8174 | TX2406994 | FEE_VARIANCE_BREACH | -1.45 | payments-partnerships | 2024-12-31 | 2025-01-02 08:53 | 46.89 | RESOLVED | 120 | OK
EXC-8442 | TX2417631 | FEE_VARIANCE_BREACH | -2.68 | payments-partnerships | 2024-12-31 |  |  | OPEN | 120
EXC-8560 | TX2421392 | ORPHANED_GATEWAY_RECORD | 553.14 | finance-ops-recon | 2024-12-31 | 2025-01-01 02:06 | 16.1 | RESOLVED | 48 | OK
EXC-8399 | TX2416092 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8508 | TX2419582 | ORPHANED_GATEWAY_RECORD | 58.02 | finance-ops-recon | 2024-12-31 | 2025-01-01 19:49 | 33.82 | RESOLVED | 48 | OK
EXC-8095 | TX2404381 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8269 | TX2410340 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8395 | TX2415990 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8051 | TX2402410 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:04 | 0.06 | RESOLVED | 1 | OK
EXC-8398 | TX2416071 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:17 | 0.29 | RESOLVED | 1 | OK
EXC-8037 | TX2401701 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8229 | TX2409072 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8623 | TX2423479 | FEE_VARIANCE_BREACH | -2.79 | payments-partnerships | 2024-12-31 | 2025-01-02 11:16 | 49.26 | RESOLVED | 120 | OK
EXC-8466 | TX2418546 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:03 | 0.06 | RESOLVED | 1 | OK
EXC-8460 | TX2418356 | ORPHANED_GATEWAY_RECORD | 243.9 | finance-ops-recon | 2024-12-31 | 2025-01-01 21:31 | 35.52 | RESOLVED | 48 | OK
EXC-8613 | TX2423218 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2024-12-31 | 2024-12-31 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8437 | TX2417370 | FEE_VARIANCE_BREACH | -0.61 | payments-partnerships | 2024-12-31 | 2025-01-03 14:14 | 76.24 | RESOLVED | 120 | OK
EXC-8407 | TX2416370 | UNCLASSIFIED_VARIANCE | -3 | recon-lead | 2024-12-31 | 2025-01-02 06:54 | 44.9 | RESOLVED | 24 | BREACH
EXC-8477 | TX2418889 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:17 | 0.28 | RESOLVED | 1 | OK
EXC-8148 | TX2406114 | FEE_VARIANCE_BREACH | -1.63 | payments-partnerships | 2025-01-01 | 2025-01-03 12:05 | 50.08 | RESOLVED | 120 | OK
EXC-8416 | TX2416742 | FEE_VARIANCE_BREACH | -1.85 | payments-partnerships | 2025-01-01 | 2025-01-03 14:52 | 52.87 | RESOLVED | 120 | OK
EXC-8159 | TX2406541 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:12 | 0.2 | RESOLVED | 1 | OK
EXC-8656 | TX2425157 | FEE_VARIANCE_BREACH | -1.64 | payments-partnerships | 2025-01-01 |  |  | OPEN | 120
EXC-8499 | TX2419367 | FEE_VARIANCE_BREACH | -1.11 | payments-partnerships | 2025-01-01 |  |  | OPEN | 120
EXC-8056 | TX2402602 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:16 | 0.27 | RESOLVED | 1 | OK
EXC-8506 | TX2419551 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8424 | TX2417055 | ORPHANED_GATEWAY_RECORD | 509.79 | finance-ops-recon | 2025-01-01 | 2025-01-02 10:55 | 24.91 | RESOLVED | 48 | OK
EXC-8624 | TX2423547 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:18 | 0.29 | RESOLVED | 1 | OK
EXC-8367 | TX2414492 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:21 | 0.35 | RESOLVED | 1 | OK
EXC-8025 | TX2401377 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8297 | TX2411299 | FEE_VARIANCE_BREACH | -2.27 | payments-partnerships | 2025-01-01 | 2025-01-03 18:40 | 56.66 | RESOLVED | 120 | OK
EXC-8124 | TX2405258 | ORPHANED_GATEWAY_RECORD | 177.01 | finance-ops-recon | 2025-01-01 | 2025-01-02 08:27 | 22.45 | RESOLVED | 48 | OK
EXC-8626 | TX2423617 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:15 | 0.25 | RESOLVED | 1 | OK
EXC-8581 | TX2422226 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:24 | 0.41 | RESOLVED | 1 | OK
EXC-8216 | TX2408688 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:12 | 0.19 | RESOLVED | 1 | OK
EXC-8591 | TX2422487 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:26 | 0.43 | RESOLVED | 1 | OK
EXC-8630 | TX2423877 | FEE_VARIANCE_BREACH | -1.32 | payments-partnerships | 2025-01-01 | 2025-01-02 04:14 | 18.23 | RESOLVED | 120 | OK
EXC-8198 | TX2407915 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:04 | 0.06 | RESOLVED | 1 | OK
EXC-8609 | TX2423044 | ORPHANED_GATEWAY_RECORD | 316.81 | finance-ops-recon | 2025-01-01 | 2025-01-02 01:16 | 15.26 | RESOLVED | 48 | OK
EXC-8041 | TX2401918 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-01 | 2025-01-01 10:03 | 0.05 | RESOLVED | 1 | OK
EXC-8118 | TX2405104 | FEE_VARIANCE_BREACH | -0.69 | payments-partnerships | 2025-01-01 |  |  | OPEN | 120
EXC-8207 | TX2408206 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:06 | 0.1 | RESOLVED | 1 | OK
EXC-8413 | TX2416661 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:07 | 0.12 | RESOLVED | 1 | OK
EXC-8226 | TX2409011 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:09 | 0.15 | RESOLVED | 1 | OK
EXC-8476 | TX2418866 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8074 | TX2403415 | FEE_VARIANCE_BREACH | -2.58 | payments-partnerships | 2025-01-02 |  |  | OPEN | 120
EXC-8238 | TX2409442 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:20 | 0.33 | RESOLVED | 1 | OK
EXC-8066 | TX2402953 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:05 | 0.09 | RESOLVED | 1 | OK
EXC-8050 | TX2402382 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:14 | 0.24 | RESOLVED | 1 | OK
EXC-8251 | TX2409931 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8491 | TX2419124 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:23 | 0.38 | RESOLVED | 1 | OK
EXC-8158 | TX2406519 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:14 | 0.23 | RESOLVED | 1 | OK
EXC-8253 | TX2410017 | FEE_VARIANCE_BREACH | -2.13 | payments-partnerships | 2025-01-02 |  |  | OPEN | 120
EXC-8276 | TX2410567 | FEE_VARIANCE_BREACH | -1.62 | payments-partnerships | 2025-01-02 |  |  | OPEN | 120
EXC-8646 | TX2424632 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:11 | 0.19 | RESOLVED | 1 | OK
EXC-8235 | TX2409262 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-02 | 2025-01-02 10:11 | 0.18 | RESOLVED | 1 | OK
EXC-8049 | TX2402324 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-03 | 2025-01-03 10:13 | 0.22 | RESOLVED | 1 | OK
EXC-8434 | TX2417307 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-03 | 2025-01-03 10:08 | 0.14 | RESOLVED | 1 | OK
EXC-8679 | TX2425942 | TIMING_MISMATCH_TIMEZONE | 0 | finance-ops-recon | 2025-01-03 | 2025-01-03 10:10 | 0.16 | RESOLVED | 1 | OK

## KPI Tracker
KPI | Value | Definition / note
Total settlements reconciled (Dec 2024) | 26000 | Input from reconciliation run
Exceptions raised | 680
Matched without exception | 25320
Match rate | 97.38% | Matched / total
Exceptions resolved | 672
Exceptions still open | 8
Median clearance velocity (working hours) | 0.32 | Weekends excluded
Fee-variance exceptions | 152 | Count; median by flag is on the dashboard
SLA breaches | 65
SLA breach rate (of resolved) | 9.673%
Net variance across exceptions (AED) | 11697.99
Absolute variance across exceptions (AED) | 44643.29
Exceptions by flag
TIMING_MISMATCH_TIMEZONE | 385
FEE_VARIANCE_BREACH | 152
ORPHANED_GATEWAY_RECORD | 72
ORPHANED_LEDGER_RECORD | 48
UNCLASSIFIED_VARIANCE | 23