# Masroof - Change Control Procedure and Log

Imran Kathat, Business Analyst

Table of Contents

# 1. Purpose

Controls changes to the approved scope baseline (69 story points, release 1.0). Simulated portfolio project. Client, people and data are fictional.

# 2. Process

- Raise: requester completes a change request (CR) with description, reason and urgency.

- Assess: BA and Engineering Lead estimate story points, schedule, cost, risk and test impact within 2 working days.

- Decide: change control board (CFO, Controller, BA, Eng Lead) decides weekly: approve, approve with conditions, defer to release 2, reject.

- Implement: approved CRs enter the backlog; BRD version and scope baseline updated; Jira ticket linked.

- Verify and close: UAT impact confirmed; CR closed with date.

# 3. Authority

| Impact | Decision authority |
| --- | --- |
| 0 SP, configuration only | Controller |
| Up to 5 SP, no date change | Controller and BA |
| More than 5 SP or date/budget impact | Board; CFO for budget or date |

# 4. Change log

| CR | Date | By | Change | Impact | Decision | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 | 2025-03-06 | Mohammed Zaid | Add Saudi riyal (SAR) as a supported currency for the Riyadh office | +3 SP, uses FX service; no date impact | Approved | Implemented 2025-03-21 |
| CR-002 | 2025-03-12 | Vikram Shetty | Add per-diem allowances by country | +13 SP, new epic, delays go-live 3 weeks | Rejected for release 1, added to release 2 backlog | Closed |
| CR-003 | 2025-03-10 | Reem Bakr | Raise second approval tier from AED 3,000 to AED 5,000 | 0 SP; policy configuration (MAS-103); test data update | Approved | Implemented 2025-03-14 |
| CR-004 | 2025-04-22 | Hana Ibrahim | Add legal-hold flag to document retention | +2 SP | Approved | Implemented 2025-04-30 |
| CR-005 | 2025-05-08 | Joanna D’Souza | Change bank file from CSV to the bank’s fixed-width format | +3 SP; UAT re-test of MAS-108 | Approved with UAT re-test | Implemented 2025-05-14 |

Scope creep prevented: CR-002 (per-diem, +13 SP) would have delayed go-live by three weeks and was deferred. Net approved change: +8 SP absorbed within sprint capacity by moving the Could epic out.

# 5. Template

| Field | Content |
| --- | --- |
| CR ID / date |  |
| Requested by |  |
| Description and reason |  |
| Impact on scope, SP, schedule, cost, risk, tests |  |
| Decision and conditions |  |
| Baseline version updated |  |