# Masroof - Executive Status Report

Imran Kathat, Business Analyst

Table of Contents

# Executive status report - Sprint 5 / UAT readiness (2 May 2025)

Simulated portfolio project. Client, people and data are fictional.

| Dimension | RAG | Comment |
| --- | --- | --- |
| Scope | Green | 69 of 69 release-1 points complete; per-diem deferred (CR-002) |
| Schedule | Green | UAT starts 5 May as planned; go-live 26 May |
| Budget | Amber | AED 556,000 actual vs 554,000 plan (0.4% over); CPI 1.00 |
| Quality | Green | 13 defects found, all closed; 0 open S1/S2 |
| Risks | Amber | Adoption (RK-06) open; scope pressure (R-08) open |

## Sprint delivery metrics

| Sprint | Committed SP | Completed SP |
| --- | --- | --- |
| Sprint 0 - Discovery | 0 | 0 |
| MAS Sprint 1 | 16 | 16 |
| MAS Sprint 2 | 16 | 16 |
| MAS Sprint 3 | 16 | 16 |
| MAS Sprint 4 | 13 | 13 |
| MAS Sprint 5 | 8 | 8 |

Average velocity 13.8 points over five sprints (reduced during Ramadan hours); 69 points delivered.

## Defect summary

| Severity | Found | Closed |
| --- | --- | --- |
| S1 | 3 | 3 |
| S2 | 5 | 5 |
| S3 | 3 | 3 |
| S4 | 2 | 2 |

## Decisions needed

- Confirm pilot group (Dubai sales) for first live month.

- Approve training schedule 19-23 May.

## Next period

UAT execution, training, cut-over plan, hypercare roster.