# Masroof - Scope Statement

Imran Kathat, Business Analyst

Table of Contents

# Scope statement

Simulated portfolio project. Client, people and data are fictional.

## Product scope

A web and mobile platform where employees capture receipts and submit claims, managers and finance approve by policy tiers, finance validates VAT, FX and documents, the ERP is posted and reimbursements are paid by bank file, with a tamper-evident audit log.

## Deliverables

Platform release 1.0; BRD, SRS, UAT pack; admin guide; training material; Confluence space; Jira project.

## In scope (release 1.0)

| Epic | Stories | MoSCoW |
| --- | --- | --- |
| Policy-Driven Approval Workflow | MAS-101, MAS-103, MAS-110, MAS-112 | Must |
| Tax-Document Capture, Validation and Audit | MAS-104, MAS-105, MAS-109, MAS-111 | Must |
| Multi-Currency Conversion | MAS-102, MAS-106 | Should |
| ERP Posting and Reimbursement | MAS-107, MAS-108 | Should |
| Corporate Card Feed Auto-Matching | MAS-113 | Could |
| GPS Mileage and Toll Import | MAS-114 | Won’t |

## Out of scope

Per-diem allowances (CR-002, release 2), corporate card feed, GPS mileage and Salik import, payroll integration, e-invoicing submission.

## Acceptance criteria for the project

Must stories done; UAT exit criteria met; no S1/S2 defects open; audit-log verification job running; UAT sign-off by Controller and Internal Audit.

## Constraints

UAE-region hosting; Ramadan hours from 1 March 2025; budget AED 554,000; go-live 26 May 2025.

## Assumptions

HR hierarchy and leave data daily; ERP sandbox available by 24 Feb; OCR provider hosts in the UAE.

## Scope baseline and change control

Baseline v1.0 approved 14 Feb 2025 (69 story points in release 1). Any change goes through the Change Control Procedure.