## README
Masroof - simulated portfolio project. Fictional client, people and data.
Sheet | Purpose
Stakeholder Register | Influence/interest and engagement
RACI | Responsibilities per deliverable
Requirements Trace | BR/FR/NFR to story to UAT
MoSCoW Backlog | Release backlog with story points
Sprint Metrics | Velocity and defect metrics (formulas)
RAID Log | Risks, assumptions, issues, dependencies
Risk Register | Scored risk register with mitigation
Change Log | Change control decisions
UAT | Acceptance tests and results
Defects | Defect log
Defect Triage Matrix | Severity rules
Budget EVM | Planned vs actual cost with formulas

## Stakeholder Register
ID | Name (fictional) | Role | Project role | Influence | Interest | Strategy | Needs / notes
SH-01 | Khalid Al Mansoori | Chief Financial Officer | Executive sponsor | High | High | Manage closely | Approves charter, budget and go-live; wants VAT recovery and audit readiness
SH-02 | Reem Bakr | Finance Controller | Product Owner | High | High | Manage closely | Owns policy, thresholds, backlog priority
SH-03 | Vikram Shetty | Head of Procurement and Admin | Business owner of expense policy | Medium | High | Keep satisfied | Concerned about split claims and vendor spend visibility
SH-04 | Aisha Farooq | HR Business Partner | Org hierarchy and leave data owner | Medium | Medium | Keep informed | Hierarchy sync and delegation rules
SH-05 | Tariq Mahmood | IT Director | Security and infrastructure | High | Medium | Keep satisfied | UAE-region hosting, SSO, audit-log controls
SH-06 | Joanna D'Souza | Senior Accountant (AP) | ERP posting and reimbursement runs | Medium | High | Keep informed | Journal mapping, bank file format
SH-07 | Mohammed Zaid | Head of Sales (field team) | Frequent claimants | Medium | High | Keep informed | Mobile receipt capture, foreign travel
SH-08 | Hana Ibrahim | Internal Auditor | Audit consumer | Medium | High | Keep informed | Audit log integrity, retention
SH-09 | Sergey Petrov | Engineering Lead | Delivery lead | High | High | Manage closely | Estimates, OCR and ERP risks
SH-10 | Noor Siddiqui | QA Lead | Test owner | Medium | High | Keep informed | Test data, UAT scripts
SH-11 | Imran Kathat | Business Analyst | Requirements, scope, governance | High | High | Author | Owns BRD/SRS, change control, traceability

## RACI
R=Responsible, A=Accountable, C=Consulted, I=Informed
Deliverable | CFO (Sponsor) | Controller (PO) | IT Director | Eng Lead | QA Lead | BA | Procurement | Audit
Project charter | A | R | C | C | I | R | C | I
Business case and build vs buy | A | R | C | C | I | R | C | C
Scope statement | A | R | C | C | I | R | C | I
Requirements elicitation | I | A | C | C | I | R | R | C
BRD and SRS authoring | I | A | C | C | C | R | C | C
Policy rules (tiers, categories) | C | A/R | I | I | I | C | R | C
Backlog and MoSCoW prioritization | I | A | I | C | I | R | C | I
Architecture and hosting decisions | I | C | A | R | I | C | I | C
Build and integration | I | I | C | A/R | C | C | I | I
Test strategy and acceptance tests | I | C | I | C | A/R | R | I | C
Change control board decisions | A | R | C | C | I | R | C | I
UAT execution and sign-off | I | A | I | C | C | R | R | R
Executive reporting | A | C | I | C | I | R | I | I
Go-live approval | A/R | R | C | C | C | C | I | C

## Requirements Trace
Req ID | Type | Requirement | Priority | Source | Epic / Story | UAT cases
BR-01 | Business | Reduce expense claim cycle time from submission to reimbursement | Must | CFO | MAS-E1, MAS-E4
BR-02 | Business | Recover input VAT only where a valid UAE tax invoice with TRN exists | Must | Finance Controller | MAS-E2
BR-03 | Business | Enforce approval authority by value; prevent self-approval and split claims | Must | Finance Controller | MAS-E1
BR-04 | Business | Provide an audit trail that cannot be altered unnoticed and meets retention requirements | Must | Internal Audit | MAS-E2
BR-05 | Business | Reimburse foreign-currency expenses by a defined, explainable rate rule | Should | Finance Controller | MAS-E3
FR-01 | Functional | Route each expense line to approvers by AED value tiers (1,000 / 5,000 / 25,000) | Must | Finance Controller | MAS-101 | UAT-01, UAT-02, UAT-03
FR-02 | Functional | Convert foreign-currency lines; hold payout if the AED value moves more than 2.0% from submission | Should | Finance Controller | MAS-102 | UAT-04, UAT-05, UAT-06
FR-03 | Functional | Configure policy tiers and categories with effective dates | Must | Finance Controller | MAS-103
FR-04 | Functional | Capture receipts and extract fields with confidence threshold 0.85 | Must | Employee | MAS-104 | UAT-07
FR-05 | Functional | Validate 15-digit TRN; apply full vs simplified invoice rule; set VAT recoverability | Must | Finance Analyst | MAS-105 | UAT-08
FR-06 | Functional | Maintain daily AED rates; refuse rates older than 24 hours | Should | Finance Analyst | MAS-106
FR-07 | Functional | Post approved reports to the ERP once, idempotently | Should | Accounts Payable | MAS-107 | UAT-09
FR-08 | Functional | Generate reimbursement file with control total | Should | Accounts Payable | MAS-108 | UAT-10, UAT-10R
FR-09 | Functional | Record every event in a hash-chained append-only log | Must | Internal Audit | MAS-109 | UAT-11
FR-10 | Functional | Delegate approvals during approved leave | Must | Line Manager | MAS-110 | UAT-12
FR-11 | Functional | Retain tax documents 5 years (VAT) and 7 years (Corporate Tax) in a UAE region | Must | Internal Audit | MAS-111 | UAT-13
FR-12 | Functional | Notify approvers, remind at 24 and 48 working hours, daily digest | Should | Line Manager | MAS-112
NFR-01 | Non-functional | OCR extraction p95 under 6 seconds; 20-second timeout falls back to manual entry | Must | Employee | MAS-104 | UAT-07
NFR-02 | Non-functional | ERP approval-to-journal posting under 5 seconds p95 in normal load | Should | Accounts Payable | MAS-107 | UAT-09
NFR-03 | Non-functional | All data and logs hosted in a UAE cloud region (PDPL alignment) | Must | IT Director | MAS-109, MAS-111 | UAT-11, UAT-13
NFR-04 | Non-functional | SSO with the corporate identity provider; role-based access | Must | IT Director | MAS-101 | UAT-01, UAT-02, UAT-03
NFR-05 | Non-functional | Mobile web and native mobile on current iOS and Android; WCAG 2.1 AA for web | Should | Employee | MAS-104 | UAT-07

## MoSCoW Backlog
Rank | Key | Epic | Story | Persona | MoSCoW | SP | Sprint | Status
1 | MAS-101 | MAS-E1 | Multi-tier approval for expense lines above AED 1,000 | Finance Controller | Must | 8 | MAS Sprint 2 | Done
2 | MAS-102 | MAS-E3 | Foreign-currency expenses with FX tolerance and tax-document enforcement | Finance Analyst | Should | 8 | MAS Sprint 3 | Done
3 | MAS-103 | MAS-E1 | Approval policy configuration for administrators | Finance Controller | Must | 5 | MAS Sprint 1 | Done
4 | MAS-104 | MAS-E2 | Receipt upload with OCR extraction | Employee | Must | 8 | MAS Sprint 1 | Done
5 | MAS-105 | MAS-E2 | TRN validation and VAT recoverability | Finance Analyst | Must | 5 | MAS Sprint 2 | Done
6 | MAS-106 | MAS-E3 | FX rate service with staleness guard | Finance Analyst | Should | 5 | MAS Sprint 3 | Done
7 | MAS-107 | MAS-E4 | Post approved expenses to the ERP as journals | Accounts Payable | Should | 8 | MAS Sprint 5 | Done
8 | MAS-108 | MAS-E4 | Generate bank reimbursement file | Accounts Payable | Should | 5 | MAS Sprint 4 | Done
9 | MAS-109 | MAS-E2 | Tamper-evident audit log | Internal Auditor | Must | 8 | MAS Sprint 4 | Done
10 | MAS-110 | MAS-E1 | Approval delegation for leave and absence | Line Manager | Must | 3 | MAS Sprint 2 | Done
11 | MAS-111 | MAS-E2 | Retention and e-archive of tax documents | Internal Auditor | Must | 3 | MAS Sprint 1 | Done
12 | MAS-112 | MAS-E1 | Approval notifications and reminders | Line Manager | Should | 3 | MAS Sprint 3 | Done
13 | MAS-113 | MAS-E5 | Match corporate card transactions to expense claims | Finance Analyst | Could | 13 | Backlog | Backlog
14 | MAS-114 | MAS-E6 | GPS mileage tracking and Salik toll import | Field Sales Executive | Won't | 8 | Backlog | Backlog

## Sprint Metrics
Ramadan (from 1 Mar 2025) reduced capacity in Sprints 2 and 3; Eid pause 30 Mar - 4 Apr.
Sprint | Start | End | Committed SP | Completed SP | Completion % | Focus
Sprint 0 - Discovery | 2025-02-03 | 2025-02-14 | 0 | 0 | n/a | Charter, business case, BRD v0.1
MAS Sprint 1 | 2025-02-17 | 2025-02-28 | 16 | 16 | 100% | Policy config, OCR capture, retention
MAS Sprint 2 | 2025-03-03 | 2025-03-14 | 16 | 16 | 100% | Approvals, TRN/VAT, delegation (Ramadan hours)
MAS Sprint 3 | 2025-03-17 | 2025-03-28 | 16 | 16 | 100% | FX service, multi-currency, notifications
MAS Sprint 4 | 2025-04-07 | 2025-04-18 | 13 | 13 | 100% | Audit log, bank file (after Eid pause)
MAS Sprint 5 | 2025-04-21 | 2025-05-02 | 8 | 8 | 100% | ERP posting, hardening
Average velocity (Sprints 1-5) |  |  |  | 13.8
Total completed SP (release 1) |  |  |  | 69
Defects found (SIT + UAT) |  |  |  | 13
Defect density (defects per story point) |  |  |  | 0.18841

## RAID Log
ID | Type | Description | Impact (1-5) | Probability (1-5) | Score | Owner | Response / mitigation | Status | Raised
R-01 | Risk | OCR receipt extraction latency exceeds tolerance at month-end peaks | 4 | 4 | 16 | Sergey Petrov | Async queue, p95 target 6s, 20s timeout fallback to manual entry, UAE-region OCR (MAS-104) | Mitigated | 2025-02-05
D-02 | Dependency | ERP and FX-rate APIs enforce rate limits; payout runs can hit HTTP 429 | 4 | 3 | 12 | Sergey Petrov | Token bucket at 70% of limit, chunks of 50, backoff with jitter, idempotency keys (MAS-107) | Mitigated | 2025-02-05
R-03 | Risk | Audit log altered by privileged DB user | 5 | 2 | 10 | Tariq Mahmood | Append-only grants, SHA-256 hash chain, nightly verification, object-lock export (MAS-109) | Mitigated | 2025-02-06
R-04 | Risk | Ramadan working hours (from 1 Mar) reduce team capacity by about 20% | 3 | 5 | 15 | Imran Kathat | Sprint 2 and 3 commitments reduced to 16 SP; UAT scheduled after Eid | Closed | 2025-02-10
R-05 | Risk | Eid Al Fitr break (about 30 Mar - 2 Apr) interrupts Sprint 3 to 4 handover | 2 | 5 | 10 | Imran Kathat | Eid pause between Sprint 3 and Sprint 4; no work scheduled | Closed | 2025-02-10
R-06 | Risk | HR hierarchy data is incomplete, breaking approval chains | 4 | 3 | 12 | Aisha Farooq | Data clean-up sprint 0; validation report on import; fallback to department head | Mitigated | 2025-02-12
R-07 | Risk | Employees circumvent thresholds by splitting claims | 3 | 4 | 12 | Reem Bakr | Same-merchant same-day aggregation rule (MAS-101) | Closed | 2025-02-12
R-08 | Risk | Scope creep: per-diem rates, mileage and card feed requested | 3 | 4 | 12 | Imran Kathat | Change control; MoSCoW; CR-002 deferred | Open | 2025-03-10
I-01 | Issue | FX test data missing EUR rate for 29 Mar (Saturday) causing stale-rate alert | 2 | 5 | 10 | Noor Siddiqui | Rule uses last business-day rate; test fixture added | Closed | 2025-03-27
I-02 | Issue | Vendor bank file spec delivered 2 weeks late | 3 | 5 | 15 | Joanna D'Souza | Bank file built to mock spec, validated at UAT | Closed | 2025-04-14
A-01 | Assumption | Hierarchy and leave data available via HR API or daily file | 4 | 3 | 12 | Aisha Farooq | Daily CSV confirmed 11 Feb | Validated | 2025-02-05
D-01 | Dependency | UAE-region cloud subscription and SSO tenant ready by 17 Feb | 5 | 2 | 10 | Tariq Mahmood | Delivered 14 Feb | Closed | 2025-02-05

## Risk Register
ID | Category | Risk | Cause / description | Impact | Probability | Score | Mitigation | Owner | Status
RK-01 | Technical | OCR latency | Receipts take too long to process | 4 | 4 | 16 | Async OCR, timeout fallback | Sergey Petrov | Mitigated
RK-02 | Compliance | VAT recovery rejected at FTA audit | Missing TRN or invalid tax invoices | 5 | 3 | 15 | TRN validation, mandatory attachments, retention (MAS-105, MAS-111) | Reem Bakr | Mitigated
RK-03 | Security | Audit-log tampering | Altered approval history | 5 | 2 | 10 | Hash chain, WORM export | Tariq Mahmood | Mitigated
RK-04 | Data residency | Receipts leave UAE region | OCR or storage vendor hosts abroad | 4 | 2 | 8 | UAE-region services only; contract check before go-live | Tariq Mahmood | Mitigated
RK-05 | Delivery | Capacity loss in Ramadan and Eid | Fewer productive hours | 3 | 5 | 15 | Reduced sprint commitments, Eid pause | Imran Kathat | Closed
RK-06 | Adoption | Employees keep using spreadsheets | Low usage after go-live | 4 | 3 | 12 | Champions in each office, training, policy cut-over date | Reem Bakr | Open
RK-07 | Integration | ERP rate limiting causes partial postings | Duplicate or missing journals | 4 | 3 | 12 | Idempotency, chunking, resume | Sergey Petrov | Mitigated
RK-08 | Finance | FX movement between submission and payout | Reimbursement differs from approval | 3 | 4 | 12 | Tolerance hold, rate rule (MAS-102) | Reem Bakr | Mitigated

## Change Log
CR ID | Date | Requested by | Change | Impact assessment | Decision | Approvers | Status
CR-001 | 2025-03-06 | Mohammed Zaid | Add Saudi riyal (SAR) as a supported currency for the Riyadh office | +3 SP, uses FX service; no date impact | Approved | Controller, Eng Lead, BA | Implemented 2025-03-21
CR-002 | 2025-03-12 | Vikram Shetty | Add per-diem allowances by country | +13 SP, new epic, delays go-live 3 weeks | Rejected for release 1, added to release 2 backlog | CFO, Controller | Closed
CR-003 | 2025-03-10 | Reem Bakr | Raise second approval tier from AED 3,000 to AED 5,000 | 0 SP; policy configuration (MAS-103); test data update | Approved | Controller, Internal Audit | Implemented 2025-03-14
CR-004 | 2025-04-22 | Hana Ibrahim | Add legal-hold flag to document retention | +2 SP | Approved | Controller, Audit | Implemented 2025-04-30
CR-005 | 2025-05-08 | Joanna D'Souza | Change bank file from CSV to the bank's fixed-width format | +3 SP; UAT re-test of MAS-108 | Approved with UAT re-test | Controller, Eng Lead | Implemented 2025-05-14

## UAT
Case | Story | Scenario | Type | Tester | Result | Date
UAT-01 | MAS-101 | Boundary: AED 1,000.00 needs one approver; AED 1,000.01 needs two | Functional | Reem Bakr | Pass | 2025-05-06
UAT-02 | MAS-101 | Split same-merchant claims aggregated | Functional | Vikram Shetty | Pass | 2025-05-06
UAT-03 | MAS-101 | Self-approval blocked | Negative | Hana Ibrahim | Pass | 2025-05-06
UAT-04 | MAS-102 | EUR line within 2% tolerance paid at payout rate | Functional | Joanna D'Souza | Pass | 2025-05-07
UAT-05 | MAS-102 | EUR line beyond tolerance held for review | Functional | Joanna D'Souza | Pass | 2025-05-07
UAT-06 | MAS-102 | Missing attachment above AED 250 blocks submission | Negative | Mohammed Zaid | Pass | 2025-05-07
UAT-07 | MAS-104 | Receipt photo extracted; low-confidence fields flagged | Functional | Mohammed Zaid | Pass | 2025-05-08
UAT-08 | MAS-105 | Missing TRN sets recoverable VAT to zero | Functional | Joanna D'Souza | Pass | 2025-05-08
UAT-09 | MAS-107 | Retry after timeout posts one journal | Functional | Joanna D'Souza | Pass | 2025-05-09
UAT-10 | MAS-108 | Payment file excludes held and invalid IBAN lines | Functional | Joanna D'Souza | Fail | 2025-05-14
UAT-10R | MAS-108 | Retest after fixed-width format fix (DEF-012) | Retest | Joanna D'Souza | Pass | 2025-05-15
UAT-11 | MAS-109 | Edited audit record detected by verification job | Security | Hana Ibrahim | Pass | 2025-05-12
UAT-12 | MAS-110 | Approval auto-delegated during leave | Functional | Aisha Farooq | Pass | 2025-05-12
UAT-13 | MAS-111 | Document deletion blocked within retention | Compliance | Hana Ibrahim | Pass | 2025-05-13

## Defects
ID | Title | Severity | Priority | Found in | Story | Status | Found | Fixed | Root cause
DEF-001 | Approval chain skipped department head at AED 1,000.01 | S1 | P1 | SIT | MAS-101 | Closed | 2025-03-05 | 2025-03-06 | Boundary used >= instead of >
DEF-002 | OCR crashed on HEIC photos from iPhones | S2 | P1 | SIT | MAS-104 | Closed | 2025-02-25 | 2025-02-28 | Unsupported format conversion
DEF-003 | Arabic supplier names garbled in report | S2 | P2 | SIT | MAS-104 | Closed | 2025-02-27 | 2025-03-04 | Wrong encoding on export
DEF-004 | Approver could approve own claim by direct URL | S1 | P1 | SIT | MAS-101 | Closed | 2025-03-07 | 2025-03-10 | Authorisation checked in UI only
DEF-005 | VAT recoverable shown for foreign supplier | S2 | P2 | SIT | MAS-105 | Closed | 2025-03-12 | 2025-03-14 | Country not evaluated
DEF-006 | FX payout used submission rate | S2 | P1 | SIT | MAS-102 | Closed | 2025-03-24 | 2025-03-26 | Wrong rate column
DEF-007 | USD lines flagged for FX review (peg ignored) | S3 | P2 | SIT | MAS-102 | Closed | 2025-03-25 | 2025-03-27 | Peg rule missing
DEF-008 | Delegation did not apply to tasks already assigned | S3 | P3 | SIT | MAS-110 | Closed | 2025-03-18 | 2025-03-24 | Assignment time rule only
DEF-009 | Audit verification job timed out above 500k rows | S3 | P3 | SIT | MAS-109 | Closed | 2025-04-16 | 2025-04-22 | Missing index on sequence
DEF-010 | Duplicate journal after ERP timeout | S1 | P1 | SIT | MAS-107 | Closed | 2025-04-28 | 2025-04-30 | Idempotency key not reused
DEF-011 | Reminder sent on Saturday | S4 | P4 | SIT | MAS-112 | Closed | 2025-04-02 | 2025-04-09 | Calendar days used
DEF-012 | Bank file rejects fixed-width lengths | S2 | P1 | UAT | MAS-108 | Closed | 2025-05-14 | 2025-05-15 | Spec change CR-005
DEF-013 | Dashboard total off by AED 0.01 on rounding | S4 | P4 | UAT | MAS-107 | Closed | 2025-05-12 | 2025-05-16 | Rounding per line vs report

## Defect Triage Matrix
Severity | Definition | Priority / action | Response SLA | Fix SLA
S1 Critical | Wrong money, security bypass, data loss | P1 - fix before next build, stop-ship | Same day | 4 hours
S2 Major | Core rule wrong, workaround exists | P1/P2 - current sprint | 1 working day | 2 working days
S3 Moderate | Edge-case defect, no money impact | P2/P3 - next sprint | 2 working days | Next sprint
S4 Minor | Cosmetic or logging | P4 - backlog | 3 working days | Backlog

## Budget EVM
Simulated cost data in AED. CPI = planned value earned / actual cost; all planned work completed so EV = BAC.
Phase | Planned AED | Actual AED | Variance AED
Sprint 0 | 42000 | 41000 | -1000
Sprint 1 | 88000 | 91000 | 3000
Sprint 2 | 88000 | 86000 | -2000
Sprint 3 | 88000 | 90000 | 2000
Sprint 4 | 88000 | 87000 | -1000
Sprint 5 | 88000 | 92000 | 4000
UAT & go-live | 72000 | 69000 | -3000
Total | 554000 | 556000 | 2000
Cost performance index (CPI) | 0.9964
Cost variance % | 0.361%