## README
Mirsad - simulated portfolio project. Fictional client, synthetic data.
Sheet | Purpose
KPI Definitions | Uniform KPI glossary signed by Head of Finance Ops
Stakeholder Register
RACI
Requirements Trace | BR/FR/NFR to story to UAT
Backlog | Prioritized backlog
Sprint Metrics | Velocity with formulas
RAID Log
Change Log
UAT
Defects
Defect Triage Matrix
Data Quality Runs | Weekly pipeline results

## KPI Definitions
KPI | Definition | Scope / rule | Unit | Source tables | Interpretation
Clearance velocity | Median elapsed hours from opened_at to resolved_at with Saturday and Sunday hours removed (24h days on working days) | Resolved tickets only | Hours | Fact_DiscrepancyResolution | Lower is better; SLA reference 24h
Daily resolution rate | Tickets resolved on the day / tickets opened on the day | Working days only; resolved by resolved_date_key | % | Fact_DiscrepancyResolution, Dim_Date | Above 100% means backlog burn-down
Margin variance % | (Actual margin - Budgeted margin) / ¦Budgeted margin¦ | Month grain and above | % | Fact_DiscrepancyResolution, Fact_BudgetAllocation | Positive is favourable
Resource utilization % | Booked hours / available hours; available = FTE x working days x 8 | Month and team | % | Fact_ResourceUtilization | Target band 75-90%
Net variance AED | Sum of (actual amount - expected amount) | All loaded tickets | AED | Fact_DiscrepancyResolution | Negative means under-recovery
Quarantine rate | Quarantined rows / rows loaded from the export | Per run | % | Pipeline log | Target under 3% after source fixes

## Stakeholder Register
ID | Name (fictional) | Role | Project role | Influence | Interest | Strategy | Needs
SH-01 | Lina Haddad | COO (regional operations) | Executive sponsor | High | High | Manage closely | Wants one definition of performance across commercial and operations
SH-02 | Reem Khan | Head of Finance Operations | Product owner | High | High | Manage closely | Owns KPI definitions and budget table
SH-03 | Arjun Nair | Head of Payments Operations | Key user | Medium | High | Keep informed | Needs clearance velocity per team
SH-04 | Mariam Youssef | Fulfilment Manager, Dubai Hub | Key user | Medium | High | Keep informed | Needs utilization and resolution rate
SH-05 | Karim Salem | Commercial Manager | Margin owner | High | Medium | Keep satisfied | Margin variance vs budget by team
SH-06 | Priyanka Rao | BI / Data Lead | Platform owner | Medium | High | Keep informed | Power BI workspace, refresh, RLS
SH-07 | Bilal Ahmed | IT Security | Access control | Medium | Low | Keep satisfied | Row-level security and data classification
SH-08 | Imran Kathat | Business Analyst | Requirements, KPI definitions, data model, UAT | High | High | Author | Owns definitions and traceability

## RACI
Deliverable | COO (Sponsor) | Head Fin Ops (PO) | BI Lead | IT Security | Ops Managers | BA
Requirements elicitation | I | A | C | I | C | R
KPI definitions and data dictionary | I | A | C | I | C | R
Data model design | I | C | A | C | I | R
Pipeline build (Python) | I | I | A/R | I | I | C
DAX measures | I | C | A/R | I | I | R
Dashboard design sign-off | A | R | C | I | C | R
Security (RLS) | I | I | R | A | I | C
UAT | I | A | C | I | R | R
Go-live | A | R | C | C | I | C

## Requirements Trace
Req ID | Type | Requirement | Priority | Source | Epic / Story | UAT cases
BR-01 | Business | One uniform definition for each operational KPI across commercial and operations teams | Must | COO | MIR-E2, MIR-E3
BR-02 | Business | Remove manual spreadsheet maintenance from weekly reporting | Must | Head Fin Ops | MIR-E1
BR-03 | Business | Leaders can see velocity, resolution rate, margin variance and utilization in one place | Must | COO | MIR-E4
FR-01 | Functional | Clean exports: parse mixed date formats, null tokens, whitespace, amounts | Must | Operations Analyst | MIR-101 | UAT-01
FR-02 | Functional | Quarantine rejected rows with reason codes; report counts | Must | Operations Manager | MIR-102 | UAT-02
FR-03 | Functional | Load star schema with surrogate keys and integrity checks | Must | BI Lead | MIR-103
FR-04 | Functional | Calendar flags Saturday-Sunday and UAE public holidays | Must | BI Lead | MIR-104
FR-05 | Functional | Clearance velocity: median working hours, weekends excluded | Must | Operations Manager | MIR-105 | UAT-03, UAT-04
FR-06 | Functional | Daily resolution rate = resolved that day / incoming that day, working days only | Must | Operations Manager | MIR-106 | UAT-05, UAT-05R
FR-07 | Functional | Margin variance % vs monthly budget by team | Must | Commercial Manager | MIR-107 | UAT-06
FR-08 | Functional | Executive dashboard with KPI cards, trend, heat map, left-rail slicers | Must | COO | MIR-108 | UAT-07
FR-09 | Functional | Excel utilization workbook | Should | Operations Manager | MIR-109 | UAT-09
FR-10 | Functional | Row-level security by team; refresh daily 06:30 GST | Must | IT Security | MIR-110 | UAT-08
NFR-01 | Non-functional | Pipeline processes 50,000 rows in under 60 seconds | Should | BI Lead | MIR-101 | UAT-01
NFR-02 | Non-functional | Dashboard opens in under 5 seconds for 12 months of data | Should | COO | MIR-108 | UAT-07
NFR-03 | Non-functional | All timestamps GST; dashboard labels state the time zone | Must | Head Fin Ops | MIR-104

## Backlog
Rank | Key | Epic | Story | Persona | MoSCoW | SP | Sprint | Status
1 | MIR-101 | MIR-E1 | Python pipeline cleans messy ticket exports | Operations Analyst | Must | 8 | MIR Sprint 1 | Done
2 | MIR-102 | MIR-E1 | Quarantine rejected rows with reasons and a quality report | Operations Manager | Must | 5 | MIR Sprint 1 | Done
3 | MIR-103 | MIR-E2 | Star schema and load | BI Developer | Must | 8 | MIR Sprint 2 | Done
4 | MIR-104 | MIR-E2 | Date dimension with UAE weekend and holidays | BI Developer | Must | 3 | MIR Sprint 1 | Done
5 | MIR-105 | MIR-E3 | Clearance velocity measure excluding weekends | Operations Manager | Must | 8 | MIR Sprint 2 | Done
6 | MIR-106 | MIR-E3 | Daily resolution rate against incoming volume | Operations Manager | Must | 5 | MIR Sprint 3 | Done
7 | MIR-107 | MIR-E3 | Margin variance vs budget allocation | Commercial Manager | Must | 5 | MIR Sprint 3 | Done
8 | MIR-108 | MIR-E4 | Executive Power BI dashboard | Executive | Must | 8 | MIR Sprint 4 | Done
9 | MIR-109 | MIR-E4 | Excel resource-utilization workbook | Operations Manager | Should | 5 | MIR Sprint 3 | Done
10 | MIR-110 | MIR-E4 | Row-level security and scheduled refresh | IT Security | Must | 5 | MIR Sprint 4 | Done

## Sprint Metrics
Average velocity excludes Sprint 0.
Sprint | Start | End | Committed SP | Completed SP | Completion % | Focus
Sprint 0 - Discovery | 2025-06-02 | 2025-06-13 | 0 | 0 | n/a | Elicitation, KPI glossary, data profiling
MIR Sprint 1 | 2025-06-16 | 2025-06-27 | 16 | 16 | 100% | Pipeline, quarantine, date dimension
MIR Sprint 2 | 2025-06-30 | 2025-07-11 | 16 | 16 | 100% | Star schema, clearance velocity
MIR Sprint 3 | 2025-07-14 | 2025-07-25 | 15 | 15 | 100% | Resolution rate, margin variance, Excel utilization
MIR Sprint 4 | 2025-07-28 | 2025-08-08 | 13 | 13 | 100% | Dashboard, RLS and refresh
Average velocity (Sprints 1-4) |  |  |  | 15
Total completed SP |  |  |  | 60

## RAID Log
ID | Type | Description | Impact (1-5) | Probability (1-5) | Score | Owner | Response | Status | Raised
R-01 | Risk | Source exports change column names or formats without notice | 4 | 4 | 16 | Priyanka Rao | Schema check at load; fail fast with message; export owner notified | Mitigated | 2025-06-03
R-02 | Risk | Teams define 'resolved' differently, so KPIs disagree | 5 | 4 | 20 | Imran Kathat | Single KPI glossary signed by Head of Finance Ops; statuses mapped in Dim_ResolutionStatus | Closed | 2025-06-04
R-03 | Risk | Median working-hours DAX is slow on large fact tables | 3 | 3 | 9 | Priyanka Rao | Parity test; materialise per-row hours in pipeline if over 1M rows | Mitigated | 2025-06-17
R-04 | Risk | Holiday calendar goes stale | 3 | 3 | 9 | Priyanka Rao | Dim_Date refreshed each December from the official UAE calendar | Open | 2025-06-05
I-01 | Issue | 7.5% of export rows rejected in first run (missing txn id, bad dates) | 3 | 5 | 15 | Imran Kathat | Quarantine report sent to export owners weekly; root-cause fixes at source | Closed | 2025-06-19
I-02 | Issue | Budget table supplied by month only; daily visuals show repeated budget | 2 | 5 | 10 | Imran Kathat | Measure returns blank below month grain (MIR-107) | Closed | 2025-07-14
A-01 | Assumption | Export is delivered daily by 06:00 GST | 4 | 2 | 8 | Reem Khan | Confirmed with export owners | Validated | 2025-06-03
D-01 | Dependency | Power BI workspace and gateway available by 16 Jun | 4 | 2 | 8 | Priyanka Rao | Provisioned 13 Jun | Closed | 2025-06-03

## Change Log
CR | Date | By | Change | Impact | Decision | Approvers | Status
CR-001 | 2025-06-24 | Karim Salem | Add resource utilization to the executive page | +5 SP (Excel workbook added, dashboard card) | Approved | Head Fin Ops, BI Lead | Implemented 2025-07-11
CR-002 | 2025-07-15 | Lina Haddad | Add weekly email PDF snapshot | +5 SP | Deferred to release 1.1 | Head Fin Ops | Closed
CR-003 | 2025-07-22 | Reem Khan | Count public holidays as non-working in resolution rate | +1 SP | Approved | Head Fin Ops | Implemented 2025-07-24

## UAT
Case | Story | Scenario | Type | Tester | Result | Date
UAT-01 | MIR-101 | Export with mixed formats cleaned correctly | Functional | Reem Khan | Pass | 2025-08-12
UAT-02 | MIR-102 | Quarantine reasons correct on 20 seeded bad rows | Functional | Reem Khan | Pass | 2025-08-12
UAT-03 | MIR-105 | Clearance velocity matches pipeline within 0.1 h | Functional | Priyanka Rao | Pass | 2025-08-13
UAT-04 | MIR-105 | Friday-to-Monday ticket gives 18.0 working hours | Functional | Arjun Nair | Pass | 2025-08-13
UAT-05 | MIR-106 | Resolution rate blank on weekends and holidays | Functional | Mariam Youssef | Fail | 2025-08-14
UAT-05R | MIR-106 | Retest after holiday fix (CR-003) | Retest | Mariam Youssef | Pass | 2025-08-15
UAT-06 | MIR-107 | Margin variance blank at day grain; correct by month | Functional | Karim Salem | Pass | 2025-08-14
UAT-07 | MIR-108 | Dashboard layout matches signed wireframe | Functional | Lina Haddad | Pass | 2025-08-18
UAT-08 | MIR-110 | Team lead sees only own team | Security | Bilal Ahmed | Pass | 2025-08-18
UAT-09 | MIR-109 | Utilization workbook ties to dashboard | Functional | Mariam Youssef | Pass | 2025-08-19

## Defects
ID | Title | Severity | Priority | Found in | Story | Status | Found | Fixed | Root cause
DEF-001 | Day-first dates parsed month-first for ambiguous dates | S2 | P1 | SIT | MIR-101 | Closed | 2025-06-18 | 2025-06-19 | Format order
DEF-002 | Duplicate tickets not quarantined | S2 | P2 | SIT | MIR-102 | Closed | 2025-06-19 | 2025-06-20 | Dedupe missing
DEF-003 | Median counted open tickets as zero | S1 | P1 | SIT | MIR-105 | Closed | 2025-07-02 | 2025-07-03 | Open rows not filtered
DEF-004 | Weekend hours not removed across multi-day tickets | S2 | P1 | SIT | MIR-105 | Closed | 2025-07-03 | 2025-07-07 | Only first weekend handled
DEF-005 | Budget repeated at day level | S3 | P3 | SIT | MIR-107 | Closed | 2025-07-14 | 2025-07-15 | Month-grain guard missing
DEF-006 | Resolution rate shown on holiday | S3 | P2 | UAT | MIR-106 | Closed | 2025-08-14 | 2025-08-15 | Holiday flag not used (CR-003)
DEF-007 | RLS mapping case-sensitive | S2 | P2 | SIT | MIR-110 | Closed | 2025-07-30 | 2025-07-31 | UPN comparison

## Defect Triage Matrix
Severity | Definition | Priority / action | Response | Fix
S1 Critical | Wrong KPI value or data leak | P1 - stop-ship | Same day | 1 working day
S2 Major | Core logic wrong in an edge case | P1/P2 - current sprint | 1 working day | 2 working days
S3 Moderate | Presentation or edge-case defect | P2/P3 - next sprint | 2 working days | Next sprint
S4 Minor | Cosmetic | P4 - backlog | 3 working days | Backlog

## Data Quality Runs
First production-like run: 2238 rows read, 2070 clean, 168 quarantined (a row can carry several reasons).
Reason | Rows | Share of export
MISSING_TXN_ID | 43 | 1.921%
UNPARSEABLE_OPENED_AT | 33 | 1.475%
NEGATIVE_TURNAROUND | 30 | 1.34%
AMOUNT_NOT_NUMERIC | 21 | 0.9383%
MISSING_TICKET_REF | 16 | 0.7149%
DUPLICATE_TICKET | 14 | 0.6256%
UNKNOWN_STATUS | 13 | 0.5809%